## SIT Testing
Test case | Description | Step Name | Description | Expected Result
1) Invoice processing | User processes documents from different sources to ERP | Step 1 | Create some invoices in Coupa & process them to ERP | Coupa invoices has been processed to ERP
|  | Step 2 | Ask for sourcesystem1 invoices from sourcesystem1 team. Request dev team to process it to ERP | sourcesystem1 file in .csv format and agreed filename has been provided by sourcesystem1 team & processed to ERP.
|  | Step 3 | Ask for sourcesystem2 invoices from sourcesystem2 team & process them to ERP | sourcesystem1 invoices were processed to ERP.
|  | Step 4 | Ask dev to run the document posting jobs | These jobs were run.
|  | Step 5 | Run the Journal Generator jobs for both AP & AM journals | Journals has been generated now & these can be verified in belonging ERP tables.
2) Invoice loading | Load and processing of referenced file | Step 1 | File loaded properly | File came in with defined amount of columns and correct amount of rows of data.
|  | Step 2 | Data formatted and columns renamed as appropriate to ensure flow through BI models | Column headings renamed and confirmed that data only contained missing data where appropriate (i.e. no data was present in that particular record).
|  | Step 3 | Validate data processing | No data was removed or dropped as was continuted to be processed by models. Invoice row count is the correct amount of rows of data (Step 1 amount - Step 2 amount).
3) Expenses processing | Load and processing of referenced file | Step 1 | File loaded properly | File came in with defined amount of columns and correct amount of rows of data.
|  | Step 2 | Data formatted and columns renamed as appropriate to ensure flow through BI models | Column headings renamed and confirmed that data only contained missing data where appropriate (i.e. no data was present in that particular record).
|  | Step 3 | Validate data processing | No data was removed or dropped as was continuted to be processed by models. Expenses row count is the correct amount of rows of data (Step 1 amount - Step 2 amount).
4) Append ERP and Expense data | Append data between two data sources | Step 1 | Append data between two data sources | Data is appended, with row count being summation of total rows for each data source and columns being a combination of similar titled columns between each data set and individual columns only appropriate for each singular data source. No data was removed or dropped as continued to be processed by models. Combination of both Invoice and Expense data is sum of test cases 2 and 3.
5) Allocation to hierarchy | Merge combined data sources with Organisation Hierarchy | Step 1 | Merge data based on defined organisational object; bringing in additional columns from Org Hierarchy BI Model | Merge valid as all items with the defined organisational object have appropriate Org level details
6) Merger with Vendor detail | Merge combined data sources with Vendor detail | Step 1 | Merge data based on Vendor Number = Vendor ID; bringing in additional columns from Org Hierarchy BI Model | Merge valid as all items with a 'Vendor Number' have approrpirate Vendor level details
7) Mapping to Period | Mapping of data sources to period | Step 1 | Merge data based on Month = Month; bring in appropriate 'Period' and 'Month' number reference | Merge valid as all items with a month (derived) by payment date where merged.
8) Mapping to Financial Year | Mapping of data sources to Financial Year | Step 1 | Merge data to ensure payment dates correspond with appropriate 'Financial Year'. | Merge valid as all remaining items have payment date with year informaiton.
9) Mapping to normalised historical (one time) vendor file | Mapping of data to normalised historical vendor file. Refers to historical data which has to be considered only one time. | Step 1 | Merge data between referenced files based on 'Vendor Id' and 'Vendor Name' | Merge between both data sets validated, with some data from new months data, not merging as they are new and not referenced in historical vendor file.
|  | Step 2 | File provided to recipient | Delivery of file via agreed data exchange SFTP
10) File load | Load and processing of referenced file | Step 1 | File loaded properly | File came in with 4 columns and 8 rows of data.
|  | Step 2 | Data formatted and columns renamed as appropriate to ensure flow through BI models | Column headings renamed and confirmed that data only contained missing data where appropriate (i.e. no data was present in that particular record).
|  | Step 3 | Added month and year reference to date listed in currency file | Appropriate month and year pulled from date (i.e. for 08/19/2019, month = Aug and year = 2019). Validation of formatting to be correct for all rows.
|  | Step 4 | Merge of currency data to Expense data | Updated model to merge data based on payment month and year and exchange rate month and year, according to requirements.
11) Inclusion and execution of spend formulas | Executing spend analysis formulas | Step 1 | Execution of 'Vendor Rank in Category' formula | Spend figure, rank and listing provided for normalised vendor's primary classification category level 1.
|  | Step 2 | Execution of 'Top Vendors' formula | Verified formula fields, referenced in 'Description' are populated according to appropriate ranking, and % breakdown.
|  | Step 3 | Execution of 'Tail' formula
|  | Step 4 | Execution of '% Tail in Category' formula
|  | Step 5 | Exectuion of 'Top/Bottom' formula
|  | Step 6 | Execution of 'Pareto' formula

## mapping
AIC_Voucher_20200211-115609 |  | expense_reports |  | AIC_Currency_Rate_20200211-115609
Original column names | Coupa Column Names | Original column names | Coupa Column Names | Original column names | Coupa Column Names
Gl Account | Account Code | Expense Report ID | Expense Report ID | From Currency | From Currency
Vendor Id | Vendor ID | Vendor Name | Vendor Name | To Currency | To Currency
Cost Center Id | Cost Centre | Expense Type | Expense Type | Date | Date
Original Currency | Currency | Account code | Account code | Rate | Exchange Rate
Invoice Number | Invoice Number | Spend Local Currency | Spend Local Currency
Original Transaction Amount | Invoice Line Amount | Currency | Currency
Canadian Dollar Equivalent Amount | Spend | Paid Date | Paid Date; Posting Date
Payment Date | Paid Date; Posting Date
Voucher Date | Voucher Date
Voucher Number | Voucher Number
Business Unit | Business Unit
Invoice Description | Invoice Line Description
Invoice Date | Invoice Date
Payment Number | Payment Number
Voucher Description | Voucher Description
Operator Id | Requisitioner
Origin | Origin
Payment Method | Payment Method
Invoice Line Number | Invoice Line Number
Dst Acct Type | Document Type