## Executive Summary
Coupa CLM: Configuration Test Scenarios
Revision History
| Version History | Date of Revision | Author | Comments
| Draft | 2019-01-22 | Ajish Chandrababu
Authorizers for Sign-Off
Summary

## Org & Templates
Organization and Templates
| Organization Legal Entity Names |  |  |  | Comments
| Name of Default Legal Entity | CytomX Therapeutics |  |  | This is the default Legal Entity name on Contracts. User can change it to one of the other Entity Names during the authoring process.
List of Contract Templates
| Template Name | Expected Test Result | Actual Result | Pass/Fail | Comments | Comments
| One Way CDA | Template should exist in Coupa
| Mutual CDA | Template should exist in Coupa
| MSA | Template should exist in Coupa
| Consulting | Template should exist in Coupa

## Process Flow Diagram
To-Be Process Flow Diagram

## Process Flow Test Scenarios
SAMPLE | Created, Executed and Filled by Customer
Step # | Role | Step Description | Expected Result | Actual Result | Pass/Fail | Comments
Request Form
1 | Contract Requester | Login to Coupa using credentials | Login Successful
2 | Contract Requester | Open Contracts Request Form | User is brought to Request Form
3 | Contract Requester | Enter relevant Contract Metadata (Requires a supplier record to be created prior to test case) | Data entered
4 | Contract Requester | Review Contract | Contract Metadata is reviewed.
5 | Contract Requester | Submit Contract | Contract is Submitted
Request Form Approval (Procurement for "New Vendor and Agreement is not CDA")
6 | Procurement | Reviews Contract Request and Approves | Form is Approved and moves onto next Approver
Request Form Approval (Contract Manager)
7 | Contract Manager | Reviews Contract Request, Assigns a Legal Associate | Legal Associate is added to approval workflow
8 | Contract Manager | Approves Contract Request | Form is Approved and moves to Legal Associate
Request Form Approval (Legal Associate)
9 | Legal Associate | Creates a Vendor in Coupa if Agreement is CDA? | Supplier is created in Coupa
10 | Legal Associate | Review and approve to start Contract Drafting | Request Form is approved
11 | Coupa | Request should auto generate the 1st draft of the contract | 1st contract draft should exist in Coupa
Create Contract
12 | Legal Associate | Click on the Contracts Tab | User is brought to Contracts Home Screen
13 | Legal Associate | Open the newly created contract and Update Contract Metadata on Contract | Contract meta data is displayed as filled in by the Requester
14 | Legal Associate | Enter relevant Contract Metadata including Supplier Name and click save | All Metadata is accepted by the system
Author Contract
15 | Legal Associate | Click 'Author Contract' button | User is brought into the Contracts Collaboration Templates page.
16 | Legal Associate | Under 'templates' select the appropriate template for this contract. | Template is chosen and the Collaboration Contract created using the template is populated with Contract meta data.
17 | Legal Associate | Click on Field on the right and fill in value for all the fields and click save | The Agreement will be updated to show the data entered
18 | Legal Associate | Click the download button | the agreements should get downloaded as a Word document
Contract Collaboration (Outside Coupa)
19 |  | Open the download contract and update it. If needed pass the document to relevant parties including supplier for collaboration and redlining | Final Draft is ready for upload into Coupa
Contract Ready for Approval
20 |  | Upload the contract by Clicking the Upload button on the Agreement Tab | Upload contract is visible on the screen
Submit Contract for Approval - All Changes Agreed
21 | Legal Associate | Click 'Submit for Approval' | Contract is sent for approval. (If there is no applicable chain, Contract is sent for review by the ultimate reviewer/approver.)
Contract Approval (Clinical Trial Contract, Leasing Agreement, NDA, Licensing, Option Agreement, MTA w/o Spend)
22 | Legal Associate | Opens the contract in Coupa | Contract opens
23 | Legal Associate | Approves Contract | Contract is ready for signature
Contract Approval (Amendment)
24 | Procurement | Opens the contract in Coupa | Contract opens
25 | Procurement | Approves Contract | Contract moves to next approver
Contract Approval (>= $100K and Not 'Licensing and Option Agreement')
26 | FP&A | Opens the contract in Coupa | Contract opens
27 | FP&A | Approves Contract | Contract moves to next approver
Contract Approval (Contract with Amount)
28 | Management Approval | Opens the contract in Coupa | Contract opens
29 | Management Approval | Approves Contract | Approval will be via Management based hierarchy of the Contract Owner. The requester will provide this name on the Contract Form. Contract Manager has the option to change that name when Contract is drafted. The approval of the contract will go up the hierarchy of Contract Owner till it finds a person with enough contract approval limit to approve the contract. After the last approver approves, the contract is ready for DocuSign Signature
DocuSign Signature
30 | Legal Associates | Click on the Review Signature button to initiate DocuSign signature process | User is taken to DocuSign after authentication
31 | Legal Associates | Enter the supplier and Customer signatory details in DocuSign and send the contract for signature | Internal and External signatory will get emails from DocuSign requesting them to sign the contract
32 | Signatory | Both Signatories signs the contract | Contract is marked signed in DocuSign
Contract Complete
33 | Coupa | DocuSign sends back signed contract and Coupa marks the contract as 'Completed' | Contract is marked as 'Completed' and locked in the system. Signatories receive an email notification with the signed PDF attached. The signed PDF is attached as the 'Legal Document' in the Contract meta data record
Publish Contract
34 | Legal Associates | Opens the contract in Coupa | Contract opens
35 | Legal Associates | Click the button 'Publish' | Contract is Published

## Custom Fields
Custom Fields (Max 20) & Relevant Standard Fields
| Field Name/Label | Field Type | On Request Form? | Comments | Type | Value | Contenet Group | Required | Hint | Expected Test Result | Actual Result | Pass/Fail | Comments

## Template Fields (hidden)
Coupa Contract Collaboration (CCC) System Configuration: Fields
| Field Details | [10 empty] | Templates (Names pulled from Org/Templates Tab)
| Field Name | Connected to Coupa Procurement* | Required in Coupa Core | Used in Contract Form | Used in Contract Metadata | Used on Contract Template | Property or Field | Required | Private | Description | Notes
Coupa Enterprise Fields
Standard Supplier Fields
| Supplier Name |  | Yes | Yes | Yes | Yes | Field | Yes | No
| Supplier Primary Address Street 1 |  | Yes | No | No | Yes | Field | Yes | No
| Supplier Primary Address City |  | Yes | No | No | Yes | Field | Yes | No
| Supplier Primary Address State |  | Yes | No | No | Yes | Field | Yes | No
| Supplier Primary Address Postal Code |  | Yes | No | No | Yes | Field | Yes | No
| Supplier Primary Contact Work Phone |  | Yes | No | No | No |  | No | No
| Supplier Primary Contact Given Name |  | Yes | No | No | No |  | No | No
| Supplier Primary Contact Family Name |  | Yes | No | No | No |  | No | No
Standard Contract Fields
| Type | N/A | Yes | No | Yes | Dropdown
| Supplier | N/A | Yes | Yes | Yes | Text
| Contract Name | N/A | Yes | No | Yes | Text
| Contract # | N/A | Yes | No | Yes | Text
| Status | N/A | Yes | No | Yes | Text
| Parent Contract | N/A | No | No | Yes | Text
| Owner | N/A | No | No | Yes | Text
| Supplier Account # | N/A | No | No | Yes | Text
| Currency | N/A | Yes | Yes | Yes | Dropdown
| Contract Start Date |  | Yes | No | Yes | Date
| Contract End Date |  | Yes | No | Yes | Date
N/A
Contract Fields: Custom (add additional Contact fields as needed. Max 20)
Contract Collaboration Fields / Properties (No Limit on #)
* These are fields that flow into Contract Collaboration from the Coupa Contract record (e.g. Supplier Name)
** Required fields in Contract Collaboration must be filled in before the contract can be signed.
*** Private Fields in Contract Collaboration can only be filled in by the Coupa Customer's users and not the Supplier's users. The best practice is to make all fields private, unless there's a reason for the customer to fill in the field details
Dropdown options for above sheet. DO NOT EDIT THIS SECTION.
Field Types
Checkbox
Currency
Money
Lookup
Date
Dropdown
Number
Text
Connected to Coupa / Required / Private
Yes
N/A
No
Field or Property
Field
Property

## CLM Roles
Coupa CLM User Roles
| Name | Description | Should Approve | Contract Request Form | All Contracts | My Contracts and Contracts I am invited to | Completed Contracts | Create | Edit | Submit for Approval | Invite | Fill Fields | Sign | Template Admin | Delete Contract | Expected Test Result | Actual Result | Pass/Fail | Comments
| CLM - Requestor | Access to Request Form |  | X |  | N/A |  |  |  |  | N/A |  | N/A
| CLM - Procurement | Can see all Contracts, fill in contract fields & invite users to contracts |  | X | X | N/A |  |  | X | X | N/A |  | N/A |  | X
| CLM - Approver | Can approve contracts and signs | X |  | X | N/A |  |  |  |  | N/A |  | N/A
| CLM - Signatory | Access to all contract features except directly creating new contracts. |  |  | X | [7 empty] | X
| CLM - FP&A | Appove contract request form |  |  |  | N/A |  |  |  |  | N/A |  | N/A
| CLM - CM | All except Signature |  | X | X | N/A | X | X | X | X | N/A | X | N/A | X

## CLM Groups
Coupa CLM Groups
Content Group
| Name | Type of Access | Expected Test Result | Actual Result | Pass/Fail | Comments
Everyone
Sensitive Contracts
Groups (Used in workflow)
| Name | Description | Allow anyone to join | Allow this group or project to be added as an approver in approval chains | Content Group | Expected Test Result | Actual Result | Pass/Fail | Comments
Procurement
Contract Management
FP&A

## Other Details
Other Details
|  |  | Expected Test Result | Actual Result | Pass/Fail | Comments
| Contract Request Form Name | Award Recommendation
Approval Chain Setup
| Build approval path based on management hierarchy | No
| Build approval path based on approval chains | Yes
| Enable adding approvers and watchers | Yes
Company Information
| Require approval for contracts | Yes
| Enable DocuSign for e-signatures | Yes
| Automatically generate contract numbers | Yes
User Setup
Give Contract License
Give Contract Approval Limit
Give access to right CLM Roles
Set Contract Ultimate Approver
| Requester Contract View (for the view 'My teams contracts', Coupa will provide the steps. Individual team managers will have to setup their own view) | My approved contract
My To Do - Shown on the Home Page
My contract in processing
My teams contracts
Contract expiring in 30 days
| Force user to enter a content group on contracts | Yes
Notifications Notifications should be generated for following cases: 1. Prior to contract expiration 2. Upon contract expiration/termination 3. For consulting agreement type, expiration/termination notification should go out to IT and facilities 4. Milestone table