## Executive Summary
User Acceptance Testing - Coupa Pay
| Customer Name: |  |  |  | <Customer Logo>
Implementing Partner:
| Revision History |  |  |  |  | Modules
| Version History | Date of Revision | Author | Comments |  | Module | In Scope?
| v1.0 | 2021-01-11 | Name | Initial Draft |  | Virtual Card Optimization
Digital Payments - Invoice
Digital Payments - Expense Reimbursement
Early Pay Discount - Static
Early Pay Discount - Dynamic
Additional Integrations
[6 empty] | Integration | In Scope?
Pay Charges
Pay Invoice Payment
Pay Expense Reimbursement
Pay Statement Report
Remit-To Address
Dynamic Discounting with Pay Invoice Payments
Dynamic Discounting without Pay Invoice Payments
Static Discounting - Invoice OK2PAY Updates
| Authorizers for Sign-Off |  |  |  |  | Environments
| Role | Name | Approval Type | Signature Status | Date | URL | UAT?
|  |  | Peer Review / Sign-off |  |  | customer-dev.coupahost.com
customer-test.coupahost.com
customer-stage.coupahost.com
[6 empty] | customer.coupahost.com | No

## Test Case Summary
Test Case # | Test Case Description | Test Script # | Test Category | Test Scenarios | Tester | Status
1 | Virtual Cards | 1.1 | Card on PO | Virtual Card on PO to Supplier - Virtual Card sent to Supplier via email (Supplier accepts to receive the card details via email) |  | Not Started
|  | 1.2 | Card on PO | Virtual Card on PO to Supplier - Virtual Card sent to Supplier via email (Supplier does NOT accept to receive the card details via email) |  | Not Started
|  | 1.3 | Card on PO | Virtual Card on PO to Supplier - Virtual Card sent to Supplier via cXML |  | Not Started
|  | 1.4 | Card on PO | Virtual Card on PO to Requester (aka One-Time Supplier) - Virtual Card provided to Requester (Supplier record does NOT exist in Coupa) |  | Not Started
|  | 1.5 | Card on PO | Virtual Card on PO to Requester (aka One-Time Supplier) - Request Virtual Card On Behalf of another User |  | Not Started
|  | 1.6 | Card on PO | Virtual Card on PO to Requester (aka One-Time Supplier) - Create PO Change to update Virtual Card amount |  | Not Started
|  | 1.7 | Card on PO | PO Virtual Card Cancellation - Cancel PO |  | Not Started
|  | 1.8 | Card on PO | PO Virtual Card Cancellation - Soft Close PO |  | Not Started
|  | 1.9 | Card on PO | PO Virtual Card Cancellation - Hard Close PO |  | Not Started
|  | 1.10 | Card on PO | Duplicate Payments Prevention - Enable Settings on Supplier Record |  | Not Started
|  | 1.11 | Card on PO | Duplicate Payments Prevention - Invoice Submissions Blocker |  | Not Started
|  | 1.12 | Card on PO | Negative Testing - Create Requisition against a COA NOT mapped to Virtual Card Payment Partner |  | Not Started
|  | 1.13 | Card on Invoice | Virtual Card on Invoice to Supplier - Virtual Card sent to Supplier via email (Supplier accepts to receive the card details via email) |  | Not Started
|  | 1.14 | Card on Invoice | Virtual Card on Invoice to Supplier - Virtual Card sent to Supplier via email (Supplier does NOT accepts to receive the card details via email) |  | Not Started
|  | 1.15 | Card on Invoice | Invoice Virtual Card Cancellation - Cancel Payment |  | Not Started
|  | 1.16 | Card on Invoice | Invoice Virtual Card Reissuance - Reissue Expired Virtual Card |  | Not Started
|  | 1.17 | Permissions | Virtual Card Roles - Virtual Card Processor |  | Not Started
|  | 1.18 | Permissions | Virtual Card Roles - Virtual Card Manager |  | Not Started
|  | 1.19 | Permissions | Virtual Card Roles - Virtual Card Admin |  | Not Started
|  | 1.20 | Reporting | Review Charges and Statement Report |  | Not Started
|  | 1.21 | Reporting | Reporting - PO Payment |  | Not Started
|  | 1.22 | Reporting | Reporting - Invoice Payments |  | Not Started
2 | Invoice Payments | 2.1 | CPA | CPA Creation - Bank Account Direct Debit Payment Type |  | Not Started
|  | 2.2 | CPA | CPA Creation - Associate CPA to COA(s) |  | Not Started
|  | 2.3 | CPA | CPA Creation - Set Default CPA(s) |  | Not Started
|  | 2.4 | CPA | CPA Creation - Notification |  | Not Started
|  | 2.5 | CPA | CPA Creation - Bank Account Digital Check Payment Type |  | Not Started
|  | 2.6 | SPA | SPA Creation - Bank Transfer |  | Not Started
|  | 2.7 | SPA | SPA Creation - Digital Check |  | Not Started
|  | 2.8 | SPA | SPA Creation - Notification |  | Not Started
|  | 2.9 | SPA | SPA Deactivation |  | Not Started
|  | 2.10 | Payment Batch | Payment Batch Creation - Remove Invoices from Coupa Pay queue |  | Not Started
|  | 2.11 | Payment Batch | Payment Batch Creation - Single Payment Batch with multiple Invoices from same supplier but billed to different COAs |  | Not Started
|  | 2.12 | Payment Batch | Payment Batch Creation - Single Payment Batch with multiple Invoices with different Payment Methods (e.g. bank transfer, digital check) |  | Not Started
|  | 2.13 | Payment Batch | Payment Batch Creation - Single Payment Batch with multiple Invoices from same Supplier but different Remit-To Addresses (i.e. different SPAs) |  | Not Started
|  | 2.14 | Payment Batch | Payment Batch Edit - Remove Invoice(s) from Draft Payment Batch |  | Not Started
|  | 2.15 | Payment Batch | Payment Batch Approval - Reject Payment Batch |  | Not Started
|  | 2.16 | Payment Batch | Payment Batch Approval - Edit Payment Batch as Approver to remove Invoice(s) from Batch |  | Not Started
|  | 2.17 | Payment Batch | Payment Batch Approval - Edit Batch as Approver to change SPA on a Payment Line |  | Not Started
|  | 2.18 | Payment Batch | Payment Batch Approval - Release Approved Payment Batch |  | Not Started
|  | 2.19 | Payment Batch | Negative Testing - Attempt to release Batch as Batch Creator |  | Not Started
|  | 2.20 | Payment Batch | Negative Testing - Attempt to release Batch when "Acting As" another User |  | Not Started
|  | 2.21 | Payment Batch | Payments - Bank Transfer Payment Successfully Completed |  | Not Started
|  | 2.22 | Payment Batch | Payments - Bank Transfer Payment Completed with Errors |  | Not Started
|  | 2.23 | Payment Batch | Payments - Digital Check Payment Successfully Completed |  | Not Started
|  | 2.24 | Payment Batch | Payment Batch Creation - Cross Border Payments (e.g. debit USD account to credit supplier's non-USD domiciled account) |  | Not Started
|  | 2.25 | Payment Batch | Payment Batch Creation - Edit Batch to adjust Invoice(s) to partially pay |  | Not Started
|  | 2.26 | Payments Cancellation | Cancel Digital Check BEFORE Supplier downloads the check from CSP |  | Not Started
|  | 2.27 | Payments Cancellation | Cancel Digital Check AFTER Supplier downloads the check from CSP |  | Not Started
|  | 2.28 | Payments Credit Note | Credit Note Creation - Create a Credit Note to apply to next Supplier Invoice |  | Not Started
3 | Expense Payments | 3.1 | CPA | CPA Creation - Bank Account Direct Debit Payment Type |  | Not Started
|  | 3.2 | CPA | CPA Creation - Associate CPA to COA(s) |  | Not Started
|  | 3.3 | CPA | CPA Creation - Set Default CPA(s) |  | Not Started
|  | 3.4 | CPA | CPA Creation - Notification |  | Not Started
|  | 3.5 | EPA | EPA Creation - Enable Coupa Pay as Employee Payment Channel on User Record |  | Not Started
|  | 3.6 | EPA | EPA Creation - Activate Employee Payment Account |  | Not Started
|  | 3.7 | EPA | EPA Deactivation |  | Not Started
|  | 3.8 | Payment Batch | Payment Batch Creation - Remove Expense Reports from Coupa Pay queue |  | Not Started
|  | 3.9 | Payment Batch | Payment Batch Creation - Single Payment Batch with multiple Expense Reports from same Employee |  | Not Started
|  | 3.10 | Payment Batch | Payment Batch Creation - Single Payment Batch with multiple Expense Reports from multiple Employees |  | Not Started
|  | 3.11 | Payment Batch | Payment Batch Edit - Remove Expense Report(s) from Draft Payment Batch |  | Not Started
|  | 3.12 | Payment Batch | Payment Batch Approval - Reject Payment Batch |  | Not Started
|  | 3.13 | Payment Batch | Payment Batch Approval - Edit Payment Batch as Approver to remove Expense Report(s) from Batch |  | Not Started
|  | 3.14 | Payment Batch | Payment Batch Approval - Release Approved Payment Batch |  | Not Started
|  | 3.15 | Payment Batch | Negative Testing - Attempt to release Batch as Batch Creator |  | Not Started
|  | 3.16 | Payment Batch | Negative Testing - Attempt to release Batch when "Acting As" another User |  | Not Started
|  | 3.17 | Payment Batch | Payments - Bank Transfer Payment Successfully Completed |  | Not Started
|  | 3.18 | Payment Batch | Payments - Bank Transfer Payment Completed with Errors |  | Not Started
4 | Static Discounting | 4.1 | CSP Invitation | CSP Registration - Invite Supplier to CSP |  | Not Started
|  | 4.2 | CSP Invitation | Static Discounting Notification |  | Not Started
|  | 4.3 | Early Payment Discount Terms | Invoice Creation - Accelerate Invoice Payment BEFORE configuring Static Discount Preferences |  | Not Started
|  | 4.4 | Early Payment Discount Terms | Invoice Creation - Accelerate Invoice Payment AFTER configuring Static Discount Preferences |  | Not Started
5 | Dynamic Discounting | 5.1 | DD Settings | DD Global Settings |  | Not Started
|  | 5.2 | DD Settings | Whitelisting Suppliers |  | Not Started
|  | 5.3 | DD Settings | Net Terms/Address |  | Not Started
|  | 5.4 | DD Settings | Invoices on DD consideration |  | Not Started
|  | 5.5 | DD Settings | Inviting Suppliers to CSP |  | Not Started
|  | 5.6 | Supplier Experience | Supplier offers "Higher APR" |  | Not Started
|  | 5.7 | Supplier Experience | Supplier offers "Lower APR" |  | Not Started
|  | 5.8 | Early Payment Discount Terms | Early Payment Request Approval - Customer approves discount offered by Supplier |  | Not Started
|  | 5.9 | Early Payment Discount Terms | Early Payment Request Approval - Customer rejects discount offered by Supplier |  | Not Started

## UAT Defects
Defect # | Test Case / Script # | Description of Issue | Expected Behavior | Coupa Transaction # (PO, Invoice, Batch) | Date Opened | Opened By | Assigned to | Severity | Status | Target Completion Date | Date Closed | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Virtual Cards
Test Script # | Test Category | Test Scenario | Role | Test Steps | Expected Result | Actual Result | Pass/Fail | Defect # | Transaction # | Tester Name | Tester's Actual Role | Test Date | Comments | Regression test applicable ?
1.1 | Card on PO | Virtual Card on PO to Supplier - Virtual Card sent to Supplier via email (Supplier accepts to receive the card details via email) | #1: Virtual Card for PO Admin #2: Virtual Card for PO Admin/Payment Account Approver #3,#4: User to create Requisitions #5,#6 : Virtual Card for PO Admin | Create New Supplier/Use existing supplier 1. Create a Supplier Payment Account - Navigate to Setup -- Suppliers -- On the Right under "Action", Click 'Add a payment account' icon -- Enter 2FA - Legal Name - Payment method - Virtual Card - Delivery method - Supplier Card - Use this account for -- PO - Coupa Pay status as Enabled - Email address -- Put suppliers email address where the cards are required to be transmitted - Days Valid - PO Payment Tolerance (%) 2. Approve Supplier Payment Account - Navigate to Setup -- Supplier Payment Account -- Click on account name -- Click on "Approve" 3. Create and approve requisition 4. PO is generated 5. PO goes on Payment Hold (Optional - Only if you have turned on PO Payment Authorization. Please check with the Partner/Coupa) 6. PO Payment Approver approves PO (Optional - Only if you have turned on PO Payment Authorization. Please check with the Partner/Coupa) 7. Card is generated and payment information is tied to PO | In Production: Supplier gets notified with the card details via secure email In UAT (testing): These emails are not being generated, however you can validate that the cards have been created by going to: Payment -> PO Payments ->> Virtual Cards or by drilling into the applicable PO
1.2 | Card on PO | Virtual Card on PO to Supplier - Virtual Card sent to Supplier via email (Supplier does NOT accept to receive the card details via email, therefore card details are emailed to AP team email address) | #1: Virtual Card for PO Admin #2: Virtual Card for PO Admin/Payment Account Approver #3,#4: User to create Requisitions #5,#6 : Virtual Card for PO Admin | Create New Supplier/Use existing supplier 1. Create a Supplier Payment Account -- follow steps in test script # 1.1 to create SPA Note: Can only have 1 SPA for this use case. Choose a different supplier than 1.1 - Delivery method: Supplier Virtual card but enter AP/Procurement email address where Customer wants to receive the cards 2. Approve Supplier Payment Account - Navigate to Setup -- Supplier Payment Account -- Click on account name -- Click on "Approve" 3. Create and approve requisition 4. PO is generated 5. PO goes on Payment Hold (Optional - Only if you have turned on PO Payment Authorization. Please check with the Partner/Coupa) 6. PO Payment Approver approves PO (Optional - Only if you have turned on PO Payment Authorization. Please check with the Partner/Coupa) 7. Card is generated and payment information is tied to PO | Case 1: User/Requester receives the card. User/Requester can use this card to pay the supplier Case 2: AP/Procurement Inbox at the customer will receive email notifying the Virtual card payment information In UAT (testing): These emails are not being generated, however you can validate that the cards have been created by going to: Payment -> PO Payments ->> Virtual Cards or by drilling into the applicable PO
1.3 | Card on PO | Virtual Card on PO to Supplier - Virtual Card sent to Supplier via cXML (Please ensure to start communications with your suppliers offline on change of payment type - This test is required to be performed with a contact at your supplier site to confirm they are able to retrieve the Card information) | #1: Virtual Card for PO Admin #2: Virtual Card for PO Admin/Payment Account Approver #3,#4: User to create Requisitions #5,#6 : Virtual Card for PO Admin | Use an existing Punchout supplier 1. Please check with Coupa if cXML setup is done in the backend for testing. 2. Ensure Supplier record has the correct PO email and the URL link 3. Create SPA for cXML suppliers -- Delivery method - cXML Virtual card - Check box: Include CVV in cXML (Optional : Check with your supplier if this is required) 4. Create Requisition 5. Requisition gets approved 6. PO is generated and is tied to Virtual Card. 7. Work with your punchout supplier offline to see if they can retrieve the payment information Note: If the supplier intends to send an Invoice into Coupa, this Invoice should be prevented from duplicate payment. Please follow steps under 1.12 to understand how these Invoices can be updated as "Fully Paid" in Coupa. | Supplier should confirm they are able to retrieve the test payment information before this is migrated into Production
1.4 | Card on PO | Virtual Card on PO to Requester (aka One-Time Supplier) - Virtual Card provided to Requester (Supplier record does NOT exist in Coupa) | #1: Virtual Card for PO Admin #2: Virtual Card for PO Admin/Payment Account Approver #3,#4: User to create Requisitions #5,#6 : Virtual Card for PO Admin | Pre-Req: The "One Time Supplier' has been setup 1. Create a SPA for "One Time Supplier" - Navigate to Setup -- Suppliers -- On the Right under "Action", Click 'Add a payment account' icon -- Enter 2FA - Payment method - Virtual Card - Delivery method - Requester Card (Internal Users/Requesters to receive the card) - Use this account for -- PO - Coupa Pay status as Enabled 2. Approve Supplier Payment Account - Navigate to Setup -- Supplier Payment Account -- Click on account name -- Click on "Approve" 3. Create requisition (Either via Forms Or creating a Request) 4. Requisition is approved and PO is generated 5. PO goes on Payment Hold (Optional - Only if you have turned on PO Payment Authorization. Please check with the Partner/Coupa) 6. PO Payment Approver approves PO (Optional - Only if you have turned on PO Payment Authorization. Please check with the Partner/Coupa) 7. Card is generated and payment information is tied to PO | User/Requester receives a card and is able to view the card information by drilling into the PO. User/Requester can use this card to pay the supplier
1.5 | Card on PO | Virtual Card on PO to Requester (aka One-Time Supplier) - Request Virtual Card On Behalf of another User | User | 1. Act on Behalf of and create a Request - Navigate to the Home page -- Click on "Write a Request" and Add to Cart -- Review the Cart -- Add "On behalf of" user 2. Create a Requisition to request a Virtual Card 3. Request goes through an approval process 4. PO gets generated and Virtual card is tied to the PO | Both the Requesters (Requester and the on behalf of user) in this case should have the ability to view the Virtual Card
1.6 | Card on PO | Virtual Card on PO to Requester (aka One-Time Supplier) - Create PO Change to update Virtual Card amount | User | 1. Pick up an already approved PO that has a Virtual card issued against 2. Click on PO -- Scroll to the bottom -- Click on "Request Change" 3. Alter the PO amount and/or quantity 4. Click on "Submit Change Request" 5. PO changes are approved 6. Validate the changes to the virtual card amount/quantity Note: PO Revisions are not allowed for Virtual Card to Supplier use case as they skip the approval process | PO must go through approval and after approval, the virtual card amount has been updated
1.7 | Card on PO | PO Virtual Card Cancellation - Cancel PO with Unused card | User | 1. Navigate to Orders -- Choose an existing approved PO that has a Virtual card issued against and ensure the Card is Valid 2. To the Right under Actions click on Cancel Icon. 3. Validate the card is no longer valid and the status of the card is Cancelled | PO canceled and virtual card 'valid to' date should become the date the PO was cancelled
1.8 | Card on PO | PO Virtual Card Cancellation - Soft Close PO with Unused Card | User | 1. Navigate to Orders -- Choose an existing approved PO that has a Virtual card issued against and ensure the Card is Valid 2. To the Right under Actions click on Soft Close icon 3. Confirm that the virtual card is cancelled and that the virtual card validity date is the current day 4. Reopen the PO and confirm the new card (with the new expiry date) is created (Only if Required) | When the PO is soft closed, card should have been cancelled via expiration/validity date When the PO is reopened, a new card should be created
1.9 | Card on PO | PO Virtual Card Cancellation - Hard Close PO | User | 1. Navigate to Orders -- Choose an existing approved PO that has a Virtual card issued against and ensure the Card is Valid 2. To the right under Actions click on Soft Close Icon 3.To the Right under Actions click on Hard Close icon 4. Confirm that the virtual card is cancelled and that the virtual card validity date is the current day | The virtual card should be cancelled via expiration date
1.1 | Card on PO (Only for Review and Understand - Nothing to execute) | Refunds after the Card is fully Charged. Please see complete article here |  | The refund will always reflect on the virtual card the refund was applied to. If Refund is issued when: 1. PO is still open : The existing active card will be adjusted Refunds/chargebacks will reflect on the virtual card available balances on the current active virtual card 2. Card was Charged partially and it expired : Refund will go back to the expired card but the current active card will be adjusted to have the appropriate amount of credit available 3. Card is fully Charged and expired: The refund will reflect on the virtual card the refund was applied to. if the PO is still open then a new card will be issued for the appropriate remaining amount. if the PO is not opened, we don’t do anything and the refund/charge comes back into the expired card and would integrate and be managed in the ERP
1.11 | Card on PO | Option 1: Submission Blocker Duplicate Payments Prevention - Enable Settings on Supplier Record | User/Coupa Admin | Note: Make sure there are controls in place On Supplier record check: 1. "Hold Invoices for AP review" 2. "Always Route Invoices from this supplier for approval" | This will put all the Invoices from this supplier on Hold. AP will need to review these invoices making sure these are not approved and processed preventing suppliers from being paid twice.
1.12 | Card on PO | Option 2: Submission Blocker Duplicate Payments Prevention - Invoice Submissions Blocker and Mark Invoices as Paid | User/Coupa Admin | 1. Create an Invoice approval Chain with a condition - Payment Channel Equals Virtual Card on PO >> In the Approval Chain, set a Submission blocking message clearly stating that “This supplier has received payment on PO and hence Invoices for this supplier should not be processed, as it would result in double paying the supplier” Please feel free to modify the blocking message as needed by the client. 2. Go to Company Info - Invoices and enable the option to "Automatically mark invoices as paid when Invoice total matches associated PO Charge Amount" to ensure the Invoices associated to a PO Payment are automatically marked as "Fully Paid" | This will prevent AP from approving Invoices that are already paid on PO's which will further prevent from double paying suppliers.
1.13 | Card on PO | Negative Testing - Create Requisition against a COA NOT mapped to Virtual Card Payment Partner | User | 1. Create request for COA not set up with a Payment Partner 2. Confirm that card cannot be created and error message 3. Change to a valid chart of accounts and confirm card Note: If virtual card suppliers can only be created with COAs with Payment Partners then this test is not applicable | Card not created with incorrect COA When changed to a valid COA, a card should be created
1.14 | Card on Invoice | Virtual Card on Invoice to Supplier - Virtual Card sent to Supplier via email (Supplier accepts to receive the card details via email) | #1,#2: Invoice Payments Admin #3: Invoice Payments Admin/Payment Account Approver #4: User to create Invoice and approve Invoice #5 : Invoice Payment Processor #6: Invoice Payment Approver #7: Invoice Payment Releaser | Need to create a Payment partner before creating a CPA. If you try choosing one randomly it will say that it already exists. 1. Create CPA for Virtual Card on Invoice - Navigate to Setup -- Company Payment Account - Click on Create - Select 'Virtual card' as Payment Type - Select your Banking partner from the drop down - Click on Create 2. Create Supplier Payment Account (Follow the above steps to create SPA) -- Delivery method - Supplier Virtual card (Put suppliers email address where the cards are required to be transmitted) 3. Approve SPA - Navigate to Setup -- Supplier Payment Account -- Click on account name -- Click on "Approve" 4. Create and approve Invoices 5. Create Payment Batch - Navigate to Payments -- Invoice Payments -- Invoices to Pay -- Select multiple Invoices with status - Ready to Pay for suppliers having Payment Methods - Virtual cards 6. Approve Payment Batch - Navigate to Payments -- Invoice Payments -- Payment Batches - Click on Payment Batch # that is in "Pending Approval" status - Click on Payment Batch # - Click on Approve 7. Release payment batch - Navigate to Payments -- Invoice Payments -- Payment Batches - Click on Payment Batch # that is in "Approved" status - Click on Release - Enter 2FA - Authorize the payment | Supplier gets notified with the Virtual card payment information on the email provided while create SPA
1.15 | Card on Invoice | Virtual Card on Invoice to Supplier - Virtual Card sent to Supplier via email (Supplier does NOT accepts to receive the card details via email) | #1,#2: Invoice Payments Admin #3: Invoice Payments Admin/Payment Account Approver #4: User to create Invoice and approve Invoice #5 : Invoice Payment Processor #6: Invoice Payment Approver #7: Invoice Payment Releaser | 1. Create Supplier Payment Account (Follow above Steps to create SPA) - Delivery Method - Supplier Virtual card (Put Ap/procurement email Id) 2. Approve SPA - Navigate to Setup -- Supplier Payment Account -- Click on account name -- Click on "Approve" 3. Create and approve Invoices 4. Create Payment Batch - Navigate to Payments -- Invoice Payments -- Invoices to Pay -- Select multiple Invoices with status - Ready to Pay for suppliers having Payment Methods - Virtual cards 5. Approve Payment Batch - Navigate to Payments -- Invoice Payments -- Payment Batches - Click on Payment Batch # that is in "Pending Approval" status - Click on Payment Batch # - Click on Approve 6. Release payment batch - Navigate to Payments -- Invoice Payments -- Payment Batches - Click on Payment Batch # that is in "Approved" status - Click on Release - Enter 2FA - Authorize the payment | AP/Procurement at the customer will receive email notifying the Virtual card payment information
1.16 | Card on Invoice | Invoice Virtual Card Cancellation - Cancel Payment | Invoice Payments Admin | 1. Create/Approve Invoice 2. Create Payment Batch -- Approve/Release Payment Batch (Follow the steps above to create/approve/release a payment batch) 3. Payment status goes into "Payment in Progress" when the supplier is notified with the Virtual card details 4. Go to Payments -- Invoice Payments -- Payments-- To the Right under Actions -- Click on Cancel the Payment by clicking on "Red Icon" | 1. This will cancel the Card and the supplier will not be able to use the card. 2. If you cancel the Card after supplier partially uses the card, Charges that were already made prior to cancelation will be processed and may appear later, but future "swipes" will be denied. Note: After the Card is completely used, cancellation/Refund on this payment is NOT possible. You could create a Credit note and set it against an open Invoice for this supplier.
1.17 | Card on Invoice | Invoice Virtual Card Reissuance - Reissue Unused Expired Virtual Card | Invoice Payments Admin | 1. Create SPA (with Days Valid) 1 day 2. Create an Invoice for this supplier that you created SPA for 3. Create a payment batch, approve and Release 4. Log into Coupa the next day to view this Payment 5. Under Payments -- Invoice Payments -- Payments search for the above invoice payment and click on Payment # 6. Click on Re-issue to issue the expired card to the suppliers | New Virtual Card will be generated and emailed out to the supplier
1.17 | Permissions | Virtual Card Roles - Virtual Card Processor | Virtual Card for PO Processor | 1. Access Coupa as a user with the Virtual Card for PO Processor role (cannot have Virtual Card Manager or Virtual Card Admin roles) 2. Go to Payments tab 3. Verify access | Access to Virtual Cards and Charge Allocations pages, but should not be able to access the Statement Reports or Charges pages
1.18 | Permissions | Virtual Card Roles - Virtual Card Manager | Virtual Card for PO Manager | 1. Access Coupa as a user with the Virtual Card for PO Manager role (cannot have Virtual Card Admin role) 2. Go to Payments tab 3. Verify access | Access to Virtual Cards, Charges, Charge Allocations and Statement Reports pages
1.19 | Permissions | Virtual Card Roles - Virtual Card Admin | Virtual Card for PO Admin | 1. Access Coupa as a user with the Virtual Card for PO Admin role 2. Go to Payments tab 3. Verify access | Access to Virtual Cards, Charges, Charge Allocations and Statement Reports pages
1.2 | Reporting | Review Charges and Statement Report | Virtual Card for PO Manager; or Virtual Card for PO Admin | 1. Ask your Coupa Project Team to generate test charges with or without statement 2. Go to Payments tab > PO Payments > Charges and review the charges 3. Go to Payments tab > Payments Hub > Statement Reports and review the statement report Note: Test the Charges integration to ERP (if applicable) | Access to Charges and Statement Reports pages to view the data
1.21 | Reporting | Reporting - PO Payment | AP |  | Understanding Reporting capabilities/Reconciliation process for PO Payments/Virtual Card Statuses
1.22 | Reporting | Reporting - Invoice Payments | AP |  | Understanding Reporting capabilities/Reconciliation process for Invoice Payments/Virtual Card Statuses
1.23 | Integrations | Integrations: Card on PO | ERP Admin | 1. PO charges for Existing suppliers to be integrated into ERP 2. PO charges for Requester Cards to be integrated into ERP
1.24 | Integrations | Integrations: Card on Invoice | ERP Admin | 1. Integrating Invoice Payments into ERP | Updating Invoice status to Paid for either of the following payment status: 1. Payment in Progress 2. Completed Successfully

## Invoice Payments
Test Script # | Test Category | Test Scenario | Role | Test Steps | Expected Result | Actual Result | Pass/Fail | Defect # | Transaction # | Tester Name | Tester's Actual Role | Test Date | Comments | Regression test applicable ?
1.1 | CPA (Pull Funds) | CPA Creation - Bank Account Direct Debit Payment Type | Invoice Payments Admin | Create a Company Payment Account of type Direct Debit 1. Navigate to Setup -- Company Payment Account 2. Click on Create 3. Select 'Bank Account' as Payment Type and choose 'Direct Debit' 4. Select 'Invoices' for using this account for 5.Enter bank account and bank address information 6. Click on Create | A successfully created Direct Debit CPA
1.2 | CPA (Push Funds) | CPA Creation - Bank Account Push Funds Payment Type | Invoice Payments Admin | Create a Company Payment Account of type Push Funds 1. Navigate to Setup -- Company Payment Account 2. Click on Create 3. Select 'Bank Account' as Payment Type and choose 'Push Funds' 4. Select 'Invoices' for using this account for 5.Enter bank account and bank address information 6. Click on Create | A successfully created Push Funds CPA
1.3 | CPA | CPA Creation - Bank Account Digital Check Payment Type | Invoice Payments Admin | Create a Company Payment Account of type Digital Check 1. Navigate to Setup -- Company Payment Account 2. Click on Create 3. Select 'Bank Account' as Payment Type and choose 'Digital Check' 4.Select 'Invoices' for using this account for 5. Completed Legal Entity information 6. Enter Digital Check Signature and Click Save 7. Complete bank account and bank address information 8. Check Positive Pay (only if in Scope) 9. Click on Create" | A successfully created Digital Check CPA
1.4 | CPA | CPA Creation - Associate CPA to COA(s) | Invoice Payments Admin | Associate a Company Payment Account to one or many Chart of Accounts 1. Navigate to Setup -- Company Payment Account 2. On the Right, click on Edit 3. Specify one or many COAs for that CPA | The CPA is now associated with one or many COAs
1.5 | CPA | CPA Creation - Set Default CPA(s) | Invoice Payments Admin | Set a default Company Payment Account for a given Chart of Accounts 1. Navigate to Setup -- Default Company Payment Account 2. On the Right, click the Edit icon for a given COA 3. Set a default CPA for the overall COA 4. Set a default CPA for each currency for the COA (may just be one) | The COA now has an overall default CPA as well as currency specific default CPAs
1.6 | CPA | CPA Creation - Notification |  | Check email for notification of newly created CPA notification | Received newly created CPA notification
1.7 | SPA | SPA Creation - Bank Transfer | Invoice Payments Admin | Create Supplier Payment Account of Bank Transfer 1.Navigate to Setup >> Suppliers 2. On the Right under "Action", Click 'Add a payment account' icon 3. Enter 2FA 4. Select payment method 'Bank Transfer' 5. Coupa Pay status as Enabled 6. Complete bank account information 7. Enter the bank address 8. Remit-To-address: Can be added newly or selected from Company remit-to 9. Click Create | A successfully created Bank Transfer SPA
1.8 | SPA | SPA Creation - Digital Check Transmitted to Supplier on CSP | Invoice Payments Admin | Create Supplier Payment Account of Digital Check 1.Navigate Setup >> Suppliers 2. On the Right under "Action", Click 'Add a payment account' icon 3. Enter 2FA 4. Select payment method >> Digital Check 5. Delivery Method : Supplier 6. Coupa Pay status >> Enabled 7. Enter the email address (Even when the digital checks will be sent to CSP, email is mandatory) 8. Remit-To-address 9. Click Create | A successfully created Digital Check SPA
1.9 | SPA | SPA Creation - Digital Check Transmitted to Buyer to download, print and mail it to supplier | Invoice Payments Admin | Create Supplier Payment Account of Digital Check 1.Navigate Setup >> Suppliers 2. On the Right under "Action", Click 'Add a payment account' icon 3. Enter 2FA 4. Select payment method >> Digital Check 5. Delivery Method : Buyer 6. Coupa Pay status >> Enabled 7. Enter the email address (Even when the digital checks will be sent to CSP, email is mandatory) 8. Remit-To-address : 9. Click Create | A successfully created Digital Check SPA
2 | SPA | SPA Creation - Notification |  | Check email for notification of newly created SPA notification | Received newly created SPA notification
2.1 | SPA | SPA Deactivation | Invoice Payments Admin | 1. Navigate to Setup >> Supplier payment accounts 2. On the Right, Click Inactivate button 3. Select 'OK' from the confirmation screen | SPA is deactivated
2.2 | Payment Batch | Payment Batch Creation - Single Payment Batch with multiple Invoices from same supplier but billed to different COAs | Invoice Payment Processor; or Invoice Payments Admin | 1. Navigate to Payments 2. Navigate to Invoice Payments 3. Select multiple Invoices with status - Ready to Pay for the same supplier but having different COA | Single Payment Batch is created with the same supplier but contains different COA's (can have different default CPAs based on set defaults)
2.3 | Payment Batch | Payment Batch Creation - Single Payment Batch with multiple Invoices with different Payment Methods (e.g. bank transfer, digital check) | Invoice Payment Processor; or Invoice Payments Admin | 1. Navigate to Payments 2. Navigate to Invoice Payments 3. Select multiple Invoices with status - Ready to Pay for suppliers having different Payment Methods - Bank transfers and Digital Checks | Single Payment Batch is created that contains Invoices with combinations of Bank transfer and Digital Checks Payment method Note: For a Digital Check payment, if you have received the checks as a Buyer, you should be able to download them in Payments -- Invoice Payments -- Digital Checks -- To the Right under Actions -- Click on Download
2.4 | Payment Batch | Payment Batch Creation - Single Payment Batch with multiple Invoices from same Supplier but different Remit-To Addresses (i.e. different SPAs) | Invoice Payment Processor; or Invoice Payments Admin | 1. Create 2 SPAs for a supplier with unique remit-to and Payment method (Digital Check and Direct Debit) 2. Create and approve at least 2 invoices with supplier (from step 1) 3. Navigate to Payments -- Invoice Payments -- Invoices to Pay 4. Select single supplier invoices (from Step 2) that are Ready to Pay with multiple SPA's for that supplier. (Ensure the Invoices are ready to Pay and are synced into ERP) 5. Check Invoices you want to Batch -- Click on "Prepare Payment Batch" 6. Click anywhere in the grey box -- Will open up for Editing SPA -- Select a different SPA than what was defaulted -- Save 7. Approve and Release Payment Batch | A single suppliers can be paid to separate accounts based invoice remittance
2.5 | Payment Batch | Payment Batch Edit - Remove Invoice(s) from Draft Payment Batch | Invoice Payment Processor; or Invoice Payments Admin | 1. Create 3 invoices for suppliers (with method - Digital Check/Direct Debit/Virtual Cards) 2. Approve Invoices 3. Create a Payment batch for all 3 Invoices (It is okay to have combinations of payment methods or with multiple COAs in this batch) 4. Save this Payment batch as a Draft 5. The status of the Payment Batch will now show as Draft 6. Go to Payment Batches -- On the Right, click on Edit for a Draft payment batch 7. Click anywhere in the grey box -- Will open up for Editing -- To the Right under "Actions" -- Click on Remove | The new Payment batch will not contain the invoices that were removed and this could be submitted for approval and will have a status as Pending approval. The Invoices that were removed will be able to be added to another new batch.
2.6 | Payment Batch | Payment Batch Approval - Reject Payment Batch | Invoice Payment Approver; or Invoice Payments Admin | 1. Navigate to Payments -- Invoice Payments -- Payment Batches 2. Click on Payment Batch # with status Pending approval. 3. Click on Reject at the bottom of the page. | The Payment batch will be rejected and the payment batch will be in a draft status for someone to correct it and send it for approval once again.
2.7 | Payment Batch | Payment Batch Approval - Edit Payment Batch as Approver to remove Invoice(s) from Batch | Edit Invoice Payment as Approver | 1. Navigate to Payments -- Invoice Payments -- Payment Batches 2. Click on Payment Batch # with status Pending approval. 3. Click Edit 4. Click anywhere in the grey box -- Will open up for Editing -- To the Right under "Action" -- Click on Remove. | The new batch will not have an invoice that was removed and this Invoice will be able to be added to the new batch
2.8 | Payment Batch | Payment Batch Approval - Release Approved Payment Batch | Invoice Payment Releaser | 1. Navigate to Payments -- Invoice Payments -- Payment Batches 2. Click on Payment Batch # that is in "Approved" status 3. Click on Release 4. Enter 2FA 5. Authorize the payment | The Payments batch is now released and the payments are now in payment initiated
2.9 | Payment Batch | Negative Testing - Attempt to release Batch as Batch Creator | Invoice Payment Releaser | 1. Payment Batch creator to create the batch 2. Invoice Payment Approver to approve the batch 3. Payment Batch creator can now attempt to release the batch | User will not be able to release the batch that they created
3 | Payment Batch | Negative Testing - Attempt to release Batch when "Acting As" another User | Invoice Payment Releaser Act As User | 1. Payment Batch creator to create the batch 2. Invoice payment approver to approve the batch 3. Payment Batch creator/approver to act as a releaser and attempt to release the payment batch | Will not be able to release the payment while in impersonation
3.1 | Payment Batch | Payments - Bank Transfer Payment Successfully Completed | Invoice Payment Processor; or Invoice Payments Admin | 1. After all the above steps, after the batches have all been released by the Releaser 2. Coordinate with Coupa Pay/Partner team to simulate a successful payment Note: Partners to create a Coupa support ticket to flip the status to "Completed Successfully". See Payment Status table for more details by scrolling further to the right | Invoices will be marked as paid and payments status will be completed successfully
3.2 | Payment Batch | Payments - Bank Transfer Payment Completed with Errors | Invoice Payment Processor; or Invoice Payments Admin | 1. Create, approve and release payment batch including bank transfer payments 2. Coordinate with Coupa Pay team to simulate a payment resulting in error 3. Review that invoices are now 'Ready to Pay' again and can be included in a new payment batch 4. Review if the SPA is deactivated - NOTE: this does not occur in TEST automatically Important Notes to remember for go live: 1. After going live, in the event of payment bouncebacks for any reason, the supplier gets notified of the payment attempt failure and the SPA will be deactivated automatically. 2. Email notifications are also sent to all users who have permissions to create Supplier Payment Accounts. Communicate with your Suppliers to get the proper remittance account details to ensure that a new SPA is submitted for review and approval prior to payment. 3. In Coupa, the status of the Payment will be updated to "Completed with Errors" and an Error Message will be provided. The related invoice(s) will also be updated back to "Ready to Pay". It is suggested that this be reviewed daily. For example, customer could set-up a schedule to run this View daily and email to designated users for review and/or action. 4. Additionally, Coupa Payment operations team will also notify the Customer contact, that will state the reasons for the payment failure which you could communicate to the supplier and request Supplier add new Remit To Account in the CSP. 5. Transfermate will return funds to the customer's bank account for the returned payment | 1. Payment status will be completed with errors and invoices will be able to be included in a new payment batch 2. SPA is inactivated (Note: in Test this will not occur due to manual updates) 3. Notifications are sent out to the suppliers and also to the SPA creators to either create a new SPA manually or communicate with your suppliers to submit correct details from CSP.
3.3 | Payment Batch | Payments - Digital Check Payment Successfully Completed | Invoice Payment Processor; or Invoice Payments Admin | 1. After all the above steps, after the batches have all been released by the Releaser 2. Act as a Supplier 3. Log into CSP with the corresponding suppliers and download digital check 4. Review digital check payment See Payment Status table for more details by scrolling further to the right | Digital check payment status will be completed successfully
3.4 | Payment Batch | Payment Batch Creation - Remove Invoices from Coupa Pay queue | Invoice Payment Processor; or Invoice Payments Admin | 1. Create and approve invoice (for a approved SPA) and make sure Invoice Payment Channel is Coupa Pay 2. Go to Payments -- Invoices to Pay -- expand the two little arrows to the right of the screen 3. Under Actions -- you will find a green toggle that can remove Invoice from Coupa Pay. 4. Turn that off | 1. This will remove invoice from Coupa Pay and the payment channel on the Invoice will be updated to ERP. 2. The Invoice will get routed to ERP to get paid.
3.5 | Payment Batch | Payment Batch Creation - Cross Border Payments (e.g. debit USD account to credit supplier's non-USD domiciled account) | Invoice Payment Processor; or Invoice Payments Admin | 1. Create an SPA in the same currency as an Invoice. For example GBP 2. Create an Invoice in a GBP currency (whichever currency the SPA was created) 3. Create a payment batch and make sure the "Pay From" Account is USD Bank account and "Pay To" is for Non USD (GBP) SPA you created in #1. 4. Release a Payment (Exchange Rate conversion should show up while authorizing the payment) | This will allow you to pay from your US bank account to an International supplier. Note: Please ensure to check if this payment is integrated into your ERP correctly.
3.6 | Payment Batch | Payment Batch Creation - Edit Batch to adjust Invoice(s) to partially pay | Invoice Payment Processor; or Invoice Payments Admin | 1. Create an Invoice for a supplier with Payment Method of either (Bank Transfer/Digital Check/Virtual Card on Invoice) 2. Create a Payment Batch and Hit one click on the Invoice that you want to Partially Pay 3. Under Actions to the right hand side, click on Adjust and put the adjustment amount that you want to pay and Click on Save 4. Approve payment batch and release payment batch 5. Coupa Support to flip the payment to "Completed Successfully" 6. The Residual amount for this Invoice will now show up in Ready to pay list for you to batch it up 7. The status of the residual invoice payment will be updated to "Partially Paid" | 1. You can now pay the Residual invoice payment that is updated to "Partial Paid" 2. Create a Payment Batch and Approve/release the batch
3.7 | Payments Cancellation | Cancel Digital Check BEFORE Supplier downloads the check from CSP |  | 1. Create and approve Invoice for Digital Check Supplier 2. Create a payment batch, approve and release the Payment batch 3. Digital Check Invoice goes into status - Payment in Progress Note: At this point until the suppliers download the digital checks from CSP, you have the ability to cancel the Invoice. 4. Under Payments -- Actions click on the Red Icon that says Cancel. | 1. The Digital check will now be cancelled and the status will be updated to Cancelled. 2. You will see this Cancelled invoice in your Ready to Pay list so you can re-batch it.
3.8 | Payments Cancellation | Cancel Digital Check AFTER Supplier downloads the check from CSP |  | 1. Create an Invoice for Digital Check Supplier 2. Create a payment batch, approve and release the Payment batch 3. Digital Check Invoice goes into status - Payment in Progress 4. Log into CSP and download the check 5. Log into Coupa and see the payment status will be now updated to "Completed Successfully" (This will update your ERP with a status as Paid) 6. Go to Payments -- Click on Cancel (Red Icon to the Right) to cancel the check after supplier downloads the check from CSP 7. Either Rebatch the Invoice to reissue a new check or Create another SPA if supplier wants to get paid via other channel | 1. This will allow you to re-batch the invoice payment and you should be able to see this in Ready to Pay list. 2. This will also allow you to reissue the check the supplier or move the suppliers to other Payment Channel if the supplier doesn't want to receive Check payments. Important Note: If Digital Checks are cancelled after they are downloaded by the suppliers, it is customers responsibility to call your bank and do a STOP Payment with your bank. Cancelling the check does not cancel the check that the supplier has already downloaded. So to avoid any double payment to the supplier, please be sure to call your back as soon as you cancel.
3.9 | Payments Credit Note | Credit Note Creation - Create a Credit Note to apply to next Supplier Invoice |  | 1. Create a Payment batch, approve and release the batch for a supplier for $100 Note: You want to create a credit note for this supplier that can be applied on the next invoice (Ensure the Remit to address on the Credit notes match with that on the Invoice) 2. Create another invoice for $200 3. Assuming you want to apply the Credit for $100, create a credit note for $100 3. Create a payment batch (the includes #2 and #3) 4. Approve the Payment batch and release it | The Supplier gets paid only for $100 for the new invoice (#2) you created.
4 |  | Payment Timing: | Here is the link-- https://success.coupa.com/Support/Docs/Core_Apps/Coupa_Pay/Announcements_and_General_Info/z_Bank_Payment_Timing
4.1 |  | Payment Status and their definitions

## Expense Payments
| Test Category | Test Scenario | Role | Test Steps | Expected Result | Actual Result | Pass/Fail | Defect # | Transaction # | Tester Name | Tester's Actual Role | Test Date | Comments | Regression test applicable ?
3.1 | CPA | CPA Creation - Bank Account Direct Debit Payment Type |  | Create a Company Payment Account of type Direct Debit 1. From Company Payment Accounts page click Create 2. Select 'Bank Account' as Payment Type and choose 'Direct Debit' 3. Select 'Expense Payments' for using this account for 4. Complete bank account and bank address information 5. Create to copmlete CPA creation | A successfully created Direct Debit CPA
3.2 | CPA | CPA Creation - Associate CPA to COA(s) |  | Associate a Company Payment Account to one or many Chart of Accounts 1. From the Company Payment Accounts page click the edit icon for a CPA 2. Specify one or many COAs for that CPA | The CPA is now associated with one or many COAs
3.3 | CPA | CPA Creation - Set Default CPA(s) |  | Set a default Company Payment Account for a given Chart of Accounts 1. From the Default Company Payment Accounts page click the edit icon for a given COA 2. Set a default CPA for the overall COA 3. Set a default CPA for each currency for the COA (may just be one) | The COA now has an overall default CPA as well as currency specific default CPAs
3.4 | CPA | CPA Creation - Notification |  | Check email for notification of newly created CPA notification | Received newly created CPA notification
3.5 | EPA | EPA Creation - Enable Coupa Pay as Employee Payment Channel on User Record | Admin | Setup a few employees you would like to test with. Following is what is needed to setup on the users profile 1. Use the right email for a user to get notified 2. Make sure to check "Expense License" under Licensing 3. Make sure to check "Expense User" for all Employees under their profile 4. Make sure to update the currency to USD 5. Flip the payment method (Employee Payment Channel) on the user profile from ERP to "Coupa Pay" | The Emlpoyee will be set up to receive notifications and be able to submit their payment information after logging into Coupa
3.6 | EPA | EPA Creation - Activate Employee Payment Account | User | 1. Employee to log into Coupa 2. Setup 2FA 3. Hover mouse on your name and navigate to settings 4. Navigate to "Employee Payment Accounts" 5. Fill in your payment information (In the test instance you can use dummy banking data. Use Routing # 123006800 for testing only) 6. Submit | Employees can setup single bank account at one time where they can receive the funds. Employees should be able to set up their payment information successfully.
3.7 | EPA | EPA Deactivation | User | 1. Login to Coupa using your user ID; on the Home page, hover over your name in the top right corner and click on Settings in the menu 2. Go to Expense Payment Account 3. Click "Deactivate" | Employee Account Payment record is inactive
3.8 | Payment Batch | Payment Batch Creation - Remove Expense Reports from Coupa Pay queue | Expense Payment Processor; or Expense Payments Admin | 1. Approve Expense Reports 2. Go to Payments -- Travel & Expense Payments -- Expenses to Pay -- expand the two little arrows to the right of the screen 3. Under Actions -- you will find a green toggle that can remove Expense Reports from being paid through Coupa Pay. 4. Turn that off | 1. This will remove Expense Report from being paid through Coupa Pay and the payment channel on the Expense Report will be updated to ERP. 2. The Expense Report will get routed to ERP to get paid.
3.9 | Payment Batch | Payment Batch Creation - Single Payment Batch with multiple Expense Reports from same Employee | Expense Payment Processor; or Expense Payments Admin | 1. Navigate to Travel & Expense Payments -- Expenses to Pay under Payments section 2. Select multiple Expense Reports with status of "Ready to Pay" for a single Employee 3. Make sure the Pay From and Pay To are pulled in correctly 4. Submit the batch for approval 5. Approve the batch 6. Release the batch 7. Work with Coupa to update the status for these payments to "Completed Successfully" so you could test integrations | Payment batch is created for multiple expense reports for a single Employee
3.10 | Payment Batch | Payment Batch Creation - Single Payment Batch with multiple Expense Reports from multiple Employees | Expense Payment Processor; or Expense Payments Admin | 1. Navigate to Travel & Expense Payments -- Expenses to Pay under Payments section 2. Select multiple Expense Reports with status of "Ready to Pay" for more than 1 Employee 3. Make sure the Pay From and Pay To are pulled in correctly for all Employees 4. Submit the batch for approval 5. Approve the batch 6. Release the batch 7. Work with Coupa to update the status for these payments to "Completed Successfully" so you could test integrations | Payment batch is created for multiple expense payments for multiple Employees in a single batch
3.11 | Payment Batch | Payment Batch Edit - Remove Expense Report(s) from Draft Payment Batch | Expense Payment Processor; or Expense Payments Admin | 1. Create a Payment batch with multiple Expense Payments 2. Save this Payment batch as a Draft 3. The status of the Payment Batch will now show as Draft 4. Pick up one of the Payment Batch with Draft status and remove one or two expense reports/payments from the batch and send the new batch for approval | The new Payment batch will not contain the Expense Report/Payment that was removed and this could be submitted for approval and will have a status as Pending approval. The Expense Report/Payment removed will be able to be added to another new batch.
3.12 | Payment Batch | Payment Batch Approval - Reject Payment Batch | Expense Payment Approver; or Expense Payments Admin | 1. Navigate to Payments Batches under the Travel & Expense Payments section. 2. Pick up a batch with status "Pending Approval". 3. Click on Reject at the bottom of the page. | The Payment batch will be rejected and the payment batch will be in a draft status for someone to correct it, rebatch it and send it for approval once again.
3.13 | Payment Batch | Payment Batch Approval - Edit Payment Batch as Approver to remove Expense Report(s) from Batch | Edit Expense Payment as Approver | 1. Navigate to Payments Batches under the Travel & Expense Payments section 2. Pick up a batch of Expense payments that has a status - Pending Approver 3. Click Edit and remove an Expense Payment from this batch and send it for approval. | The new batch will not have an Expense Payment that was removed and this Expense payment will be able to be added to the new batch
3.14 | Payment Batch | Payment Batch Approval - Release Approved Payment Batch | Expense Payment Releaser | 1. Navigate to the Payments Batch and pick up an approved batch and hit release 2. Authorize the payment | The Payments batch is now released and the payments are now in payment initiated
3.15 | Payment Batch | Negative Testing - Attempt to release Batch as Batch Creator | Expense Payment Releaser | 1. User with ability to create and release batches creates a payment batch 2. Once approved, same user that created the batch attempts to release the batch | User will not be able to release the batch that they created
3.16 | Payment Batch | Negative Testing - Attempt to release Batch when "Acting As" another User | Expense Payment Releaser Act As User | 1. Create and approve payment batch 2. Impersonate a releaser (that did not create the batch) and attempt to release the payment batch | Will not be able to release the payment while in impersonation
3.17 | Payment Batch | Payments - Bank Transfer Payment Successfully Completed | Expense Payment Processor; or Expense Payments Admin | 1. Create, approve and release Expense payment batch 2. Coordinate with Coupa Pay team to simulate a payment completing successfully - provide the Payment # 3. Review that Expense Reports do not show as "Ready to Pay" | Expense Payment status will show as "Completed Successfully"
3.18 | Payment Batch | Payments - Bank Transfer Payment Completed with Errors | Expense Payment Processor; or Expense Payments Admin | 1. Create, approve and release Expense payment batch 2. Coordinate with Coupa Pay team to simulate a payment resulting in error - provide the Payment # 3. Review that Expense Reports Payments are now in "Ready to Pay' status and can be included in a new payment batch Important Notes to remember for go live: 1. After going live in an event of payment bouncebacks due to any reason, the employee gets notified of the payment attempt failure and the EPA will be deactivated automatically. 2. A notification is sent to the person who created the Employee Payment Account when their payment account is deactivated. 3. In Coupa, the status of the Payment will be updated to "Completed with Errors" and an Error Message will be provided. The related expense report(s) will also be updated back to "Ready to Pay". It is suggested that this be reviewed daily. For example, customer could set-up a schedule to run this View daily and email to designated users for review and/or action. 4. Additionally Coupa Payment operations team will also notify the Customer contact, that will state the reasons for the payment failure which you could communicate to the employee and request your employees to log into Coupa and update their payment information accurately. 5. Transfermate will return funds to the customer's bank account for the returned payment | 1. Expense Payment status will show as "Completed with Errors" and Expense Report will be available to be included in a new payment batch 2. Expense Payment Account is inactivated (this will only occur in PROD, cannot simulate in TEST) 3. Notifications are sent out to the Employees about the payment failure (this will only occur in PROD, cannot simulate in TEST) 4. Employees to log into Coupa and update their payment account accurately

## Static Discounting
Test Script # | Test Category | Test Scenario | Role | Test Steps | Expected Result | Actual Result | Pass/Fail | Defect # | Transaction # | Tester Name | Tester's Actual Role | Test Date | Comments | Regression test applicable ?
4.1 | CSP Invitation | CSP Registration - Invite Supplier to CSP | Admin Buyer Accounts Payable | 1. Login to Coupa using your user ID; on the Home page, go to the Suppliers tab 2. Look up a supplier 3. Select the supplier by ticking the checkbox in front of the supplier name 4. At the bottom of the page, click "Invite" 5. Review the email invitation content (edit if needed), and click "Send Invite" | CSP invitation sent to supplier
4.2 | CSP Invitation | Static Discounting Notification | Admin Buyer Accounts Payable | 1. Supplier to be notified in an email that they are eligible to Accelerate their Invoices from CSP 2. Notification message needs to match with the custom message configured in Coupa. | Notification with custom content sent to suppliers
4.3 | Early Payment Discount Terms | Invoice Creation - Accelerate Invoice Payment BEFORE configuring Static Discount Preferences | Supplier | 1. Login to CSP using your supplier ID; on the Home page, go to the Invoices tab 2. Create an invoice 3. Click "Accelerate" next to the Payment Term 4. Choose the early payment discount term 5. Confirm the Payment Term is updated | Payment Term on the invoice is updated with the accelerated term chosen by the supplier
4.4 | Early Payment Discount Terms | Invoice Creation - Accelerate Invoice Payment AFTER configuring Static Discount Preferences | Supplier | 1. Login to CSP using your supplier ID; on the Home page, go to the Setup tab 2. In the Admin section, go to Payment Preferences > Static Discounting 3. Click "Edit" 4. Set preferred early payment discount terms and click "Save" 4. Go to the Invoices tab 5. Create an invoice 6. Confirm invoice is accelerated automatically | CSP auto-updates payment terms on newly created invoices based on the configured static discounting preferences

## Dynamic Discounting
Test Script # | Test Category | Test Scenario | Role | Test Steps | Expected Result | Actual Result | Pass/Fail | Defect # | Transaction # | Tester Name | Tester's Actual Role | Test Date | Comments | Regression test applicable ?
5.1 | Dynamic Discounting Settings | DD Global Settings |  | 1. Go to Setup -- Dynamic Discounting 2. Make sure the settings are all correct 3. Optional - Create another DD setting for different COA's if required | DD settings are all configured, active, and DD enabled on the Instance.
5.2 | Dynamic Discounting Settings | Whitelisting Suppliers |  | 1. Identify suppliers for DD 2. Go to Suppliers -- Edit -- Check "Whitelist for Dynamic Discounting" -- Enter Dynamic Discounting Settings | Suppliers are Whitelisted for Dynamic Discounting and their approved invoices will be eligible for DD
5.3 | Dynamic Discounting Settings | Net Terms/Address |  | 1. Ensure all DD suppliers are on Net Terms 2. Ensure all DD suppliers have US address updated in the supplier record in Coupa | Suppliers approved invoices will be eligible for DD if the COA of the invoice matches the COA of the DD setting applied to the Supplier
5.4 | Dynamic Discounting Settings | Invoices on DD consideration |  | 1. Create Invoices and Approve Invoices | Invoices will all be under "DD Consideration" The way to check is: Open Approved Invoice -- Scroll down to Payments -- Status updated "Working Capital Consideration"
5.5 | Dynamic Discounting Settings | Inviting Suppliers to CSP |  | 1. Update the Supplier record with an email address you want to be notified to activate CSP account. Note: In the test instance we recommend you provide your gmail address/office address/create a gmail account for the users to act as supplier 2. Invite supplier to CSP | Suppliers are notified with a link to activate CSP account and offer Discounts on the Invoice
5.6 | Supplier Experience | Supplier offers "Higher APR" |  | 1. Log into CSP 2. Go to Payments -- Early payments -- Eligible Invoices -- Select all Invoices where you want to offer discounts -- Click on "Get Paid" 3. Pick up a rate Higher than what is setup by the customer on Coupa. Note: If APR of 24% (2% pm) is setup on DD global settings, pick up a percentage equal to or Higher than 2% 4. Submit | Suppliers discount offer gets "Accepted and they will be able to see all of the below: 1. Expected Payment Date 2. Offer 3. Requested Amount 4. Status gets updated to "Accepted"Automatically
5.7 | Supplier Experience | Supplier offers "Lower APR" |  | 1. Log into CSP 2. Go to Payments -- Early payments -- Eligible Invoices -- Select all Invoices where you want to offer discounts -- Click on "Get Paid" 3. Pick up a rate Lower than what is setup by the customer on Coupa. Note: If APR of 24% (2% pm) is setup on DD global settings, pick up a percentage Lower than 2% 4. Submit | Suppliers discount offer goes into status " Buyer Approval Required" and they will be able to see all of the below: 1. Expected Payment Date - Blank (As this will be updated once the Buyer approves the discount offered) 2. Offer 3. Requested Amount 4. Status gets updated to " Buyer Approval Required"
5.8 | Early Payment Discount Terms | Early Payment Request Approval - Customer approves discount offered by Supplier |  | 1. Log into Coupa 2. Go to Payments -- Dynamic Discounting - Early Payment Request Status 3. Click on ID with status "Pending Approval" 4. Review the Discount offer made by the supplier 5. Click "Approve" | Supplier should be able to see the status as "Accepted" in CSP. Below are the steps to follow: 1. Log into CSP 2. Go to Payments -- Early Payments -- Payment Request 3. Status is now "Accepted"
5.9 | Early Payment Discount Terms | Early Payment Request Approval - Customer rejects discount offered by Supplier |  | 1. Repeat test script # 5.7 to submit an accelerated invoice 2. Log into Coupa 3. Go to Payments -- Dynamic Discounting - Early Payment Request Status 4. Click on ID with status "Pending Approval" 5. Review the Discount offer made by the supplier 6. Click "Reject" | Supplier should be able to see the status as "Rejected by Buyer" in CSP. Below are the steps to follow: 1. Log into CSP 2. Go to Payments -- Early Payments -- Payment Request 3. Status is now "Rejected by Buyer"

## Last Updated
Last updated 9.16.21