## Test Case Summary
Test Case Number | Test Case Desc | Test Script # | Scenarios | Tester | Status
1 | Purchase Services from a Hosted Catalog | 1.1 | Hosted Catalog - Item - Type - Resource |  | Not Started
|  | 1.2 | Hosted Catalog - Item - Type - Service Qty |  | Not Started
|  | 1.3 | Hosted Catalog - Requisition with five line items - Mixture of Resource and Service Qty |  | Not Started
2 | Purchase Services using a Free Form Requisition | 2.1 | Create a requisition - Service - Type - Resource |  | Not Started
|  | 2.2 | Create a requisition - Service - Type - Service (Qty) |  | Not Started
|  | 2.3 | Create a requisition - Service - Type - Service (Amt) |  | Not Started
|  | 2.4 | Create a requisition with 4 line items - Mixture of different service types |  | Not Started
3 | Purchase Services using Web forms | 3.1 | Create a requisition - Webform - Service - Type - Resource |  | Not Started
|  | 3.2 | Create a requisition - Webform - Service - Type - Service (Qty) |  | Not Started
|  | 3.3 | Create a requisition - Webform - Service - Type - Service (Amt) |  | Not Started
4 | Process Requisition Approvals | 4.1 | Process Approval by logging into Coupa and checking the Approver's To Do list. |  | Not Started
|  | 4.2 | Process Approval via email |  | Not Started
|  | 4.3 | Process Approval via iPhone |  | Not Started
|  | 4.4 | Process Approval via PDA |  | Not Started
|  | 4.5 | Process Approval by logging into Coupa and checking the Approver's To Do list. |  | Not Started
|  | 4.6 | Process Approval by logging into Coupa and accessing the Approver's Inbox. |  | Not Started
|  | 4.7 | Process Approval by logging into Coupa and accessing the Approver's Inbox. |  | Not Started
|  | 4.8 | Process Denial by logging into Coupa and checking the Approver's To Do list. |  | Not Started
|  | 4.9 | Process Denial by logging into Coupa and accessing the Approver's Inbox. |  | Not Started
|  | 4.10 | Process Denial by Email |  | Not Started
5 | Process Purchase Order | 5.1 | Issue cXML PO |  | Not Started
|  | 5.2 | Issue Email PO |  | Not Started
|  | 5.3 | Issue HardCopy PO and Mark as Sent |  | Not Started
|  | 5.4 | Deliver PO to Supplier set to "Prompt" |  | Not Started
|  | 5.5 | Manually Close PO |  | Not Started
6 | Service/Timesheet Entry | 6.1 | Enter Service/Timesheet for Resource using the CSP |  | Not Started
|  | 6.2 | Enter Service/Timesheet for Services Qty using the CSP |  | Not Started
|  | 6.3 | Enter Service/Timesheet for Services Amt using the CSP |  | Not Started
|  | 6.4 | Enter Service/Timesheet for Resource using the SAN |  | Not Started
|  | 6.5 | Enter Service/Timesheet for Services Qty using the SAN |  | Not Started
|  | 6.6 | Enter Service/Timesheet for Services Amt using the SAN |  | Not Started
|  | 6.7 | Try to create Service/Timesheet against PO that is soft closed |  | Not Started
|  | 6.8 | Enter a manual receipt against a service PO
7 | Process Service/Timesheet Approvals | 7.1 | Process Approval by logging into Coupa and checking the Approver's To Do list. |  | Not Started
|  | 7.2 | Process Approval via email |  | Not Started
|  | 7.3 | Reminder Notifications and Escalations (will take X hours)
|  | 7.4 | Process Denial by logging into Coupa and checking the Approver's To Do list. |  | Not Started
|  | 7.5 | Process Denial by logging into Coupa and accessing the Approver's Inbox. |  | Not Started
|  | 7.6 | Process Denial by Email |  | Not Started
8 | Invoice Processing and Matching | 8.1 | Enter Invoices against a purchase order. |  | Not Started
|  | 8.2 | Invoice for Qty greater than received |  | Not Started
|  | 8.3 | Monthly invoice against weekly timesheets |  | Not Started
|  | 8.4 | Invoice / receipt value greater than PO value |  | Not Started
|  | 8.5 | Additional charges added to invoice |  | Not Started
9 | Basic Navigation | 9.1 | Service / Timesheet tab |  | Not Started
|  | 9.2 | Service / Timesheet Lines tab |  | Not Started
|  | 9.3 | View receipt and confirmation from Order |  | Not Started

## UAT Defects
Test Case Number | Test Script Number | Issue | Coupa Transaction Number (PO, PR, Invoice Numbers) | Date Opened | Opened By | Assigned to | Status (Open, Closed, Deferred) | Target Completion Date | Date Closed | Comments
2.1 |  | Made service end date required, but not working

## Case 1 Hosted Catalogs
Test Case #2 |  | Purchase via Hosted Catalogs
Description
# | Test Scenario | Test Script | Role | Test Steps | Expected Result | Actual Result | Tester | Pass/Fail
1.1 | Hosted Catalog - Item - Type - Resource | Purchase Services from a Hosted Catalog | User | 1. Login to Coupa using your user ID; enter an item name or keyword within the 'Search Bar.' 2. Search service item 3. Build cart , defining qty of hours required for resource. 4. Once items have been added to your cart, select 'Cart.' 5. Edit the item to add Service start and end dates, resource manager(internal timesheet approver) and Service manager email (Suppliers email) 5. Verify Billing Acct and Ship to Address are properly updated. 6. Optionally enter a Justification if a note is required for the purchase (why you are buying this) 7. Click "Submit for Approval" | Requisition has been created and saved with Status 'Pending Approval'. | Enter Requisition # here: Approvers:
1.2 | Hosted Catalog - Item - Type - Service Qty | Purchase Services from a Hosted Catalog | User | 1. Login to Coupa using your user ID; enter an item name or keyword within the 'Search Bar.' 2. Search service item 3. Build cart , defining qty required for service. 4. Once items have been added to your cart, select 'Cart.' 5. Edit the item to add Service start and end dates, resource manager(internal timesheet approver) and Service manager email (Suppliers email) 5. Verify Billing Acct and Ship to Address are properly updated. 6. Optionally enter a Justification if a note is required for the purchase (why you are buying this) 7. Click "Submit for Approval" | Requisition has been created and saved with Status 'Pending Approval'. | Enter Requisition # here: Approvers:
1.3 | Hosted Catalog - Requisition with five line items - Mixture of Resource and Service Qty | Purchase Services from a Hosted Catalog | User | 1. Login to Coupa using your user ID; enter an item name or keyword within the 'Search Bar.' 2. Search service items 3. Build cart , defining the qty required 4. Once items have been added to your cart, select 'Cart.' 5. Edit the items to add Service start and end dates, resource manager(internal timesheet approver) and Service manager email (Suppliers email) 5. Verify Billing Acct and Ship to Address are properly updated. 6. Optionally enter a Justification if a note is required for the purchase (why you are buying this) 7. Click "Submit for Approval" | Requisition has been created and routed for approval. | Enter Requisition # here: Approvers:

## Case 2 FreeForm Service
Test Case #4 |  | Purchase a Service using a Free Form Requisition
Description
# | Test Scenario | Test Script | Role | Test Steps | Expected Result | Actual Result | Tester | Pass/Fail
2.1 | Create a requisition - Service - Type - Resource | Purchase Services using a Free Form Requisition | User | 1. Login to Coupa using your user ID; on the Home page, click on the Write icon at the top of the page. 2. Enter a description of a Service you need. 3. Select radio button for Service 4. Select Type 'Resource' 4. Select the vendor for that Service 5. Select the commodity for that Service. Enter details, including Price (Hourly rate) and qty (number of hours) 6. Enter Service Start and End Date 7. Enter Resource Manager (Internal manager to approve timesheet) 8. Enter Service Manager Email (Suppliers email) 9. Click "Add to Cart" 10. Click on "Review Cart" to go to Check Out 11. Verify correct billing string has defaulted for each line. Correct as required. 12. Click "Submit for Approval" | Requisition has been created and saved with Status 'Pending Approval'. | Enter Requisition # here: Approvers:
2.2 | Create a requisition - Service - Type - Service (Qty) | Purchase Services using a Free Form Requisition | User | 1. Login to Coupa using your user ID; on the Home page, click on the Write icon at the top of the page. 2. Enter a description of a Service you need. 3. Select radio button for Service 4. Select Type 'Service (Qty)' 4. Select the vendor for that Service 5. Select the commodity for that Service. Enter details, including Price, qty and UOM 6. Enter Service Start and End Date 7. Enter Resource Manager (Internal manager to approve timesheet) 8. Enter Service Manager Email (Suppliers email) 9. Click "Add to Cart" 10. Click on "Review Cart" to go to Check Out 11. Verify correct billing string has defaulted for each line. Correct as required. 12. Click "Submit for Approval" | Requisition has been created and saved with Status 'Pending Approval'. | Enter Requisition # here: Approvers:
2.3 | Create a requisition - Service - Type - Service (Amt) | Purchase Services using a Free Form Requisition | User | 1. Login to Coupa using your user ID; on the Home page, click on the Write icon at the top of the page. 2. Enter a description of a Service you need. 3. Select radio button for Service 4. Select Type 'Service (Amt)' 4. Select the vendor for that Service 5. Select the commodity for that Service. Enter details, including Price. 6. Enter Service Start and End Date 7. Enter Resource Manager (Internal manager to approve timesheet) 8. Enter Service Manager Email (Suppliers email) 9. Click "Add to Cart" 10. Click on "Review Cart" to go to Check Out 11. Verify correct billing string has defaulted for each line. Correct as required. 12. Click "Submit for Approval" | Requisition has been created and saved with Status 'Pending Approval'. | Enter Requisition # here: Approvers:
2.4 | Create a requisition with 4 line items - Mixture of different service types | Purchase Services using a Free Form Requisition | User | 1. Login to Coupa using your user ID; on the Home page, click on the Write icon at the top of the page. 2. Enter a description of a Service you need. 3. Select radio button for Service 4. Select Type 'Service (Qty)' 4. Select the vendor for that Service 5. Select the commodity for that Service. Enter details, including Price, qty and UOM 6. Enter Service Start and End Date 7. Enter Resource Manager (Internal manager to approve timesheet) 8. Enter Service Manager Email (Suppliers email) 9. Click "Add to Cart" 10. Repeat 3 more times, using all service types. 10. Click on "Review Cart" to go to Check Out 11. Verify correct billing string has defaulted for each line. Correct as required. 12. Click "Submit for Approval" | Requisition has been created and saved with Status 'Pending Approval'. | Enter Requisition # here: Approvers:

## Case 3 Web Forms
Test Case #5 |  | Web Forms
Description
# | Test Scenario | Test Script | Role | Test Steps | Expected Result | Actual Result | Tester | Pass/Fail
3.1 | Create a requisition - Webform - Service - Type - Resource | Web Forms | User | 1. Login to Coupa using your user ID; on the Home page, click on the Search icon at the top of the page. 2. Click the Web Form link for Webform #1. 3. Fill out the form and save it. 4. Click on "Review Cart" to go to Check Out 5. Verify correct additional information displays for the line item. Confirm correct Billing info. Correct as required. 6. Click "Submit for Approval" | Requisition has been created and saved with Status 'Pending Approval.' | Enter Requisition # here: Approvers:
3.2 | Create a requisition - Webform - Service - Type - Service (Qty) | Web Forms | User | 1. Login to Coupa using your user ID; on the Home page, click on the Search icon at the top of the page. 2. Click the Web Form link for Webform #2 3. Fill out the form and save it. 4. Click on "Review Cart" to go to Check Out 5. Verify correct additional information displays for the line item. Confirm correct Billing info. Correct as required. 6. Click "Submit for Approval" | Requisition has been created and saved with Status 'Pending Approval.' | Enter Requisition # here: Approvers:
3.2 | Create a requisition - Webform - Service - Type - Service (Amt) | Web Forms | User | 1. Login to Coupa using your user ID; on the Home page, click on the Search icon at the top of the page. 2. Click the Web Form link for Webform #3 3. Fill out the form and save it. 4. Click on "Review Cart" to go to Check Out 5. Verify correct additional information displays for the line item. Confirm correct Billing info. Correct as required. 6. Click "Submit for Approval" | Requisition has been created and saved with Status 'Pending Approval.' | Enter Requisition # here: Approvers:

## Case 4 Approvals
Test Case #8 |  | Process Requisition Approvals
Description
# | Test Scenario | Test Script | Role | Test Steps | Expected Result | Actual Result | Tester | Pass/Fail
4.1 | Approve Req from TC 1.1 | Process Approval by logging into Coupa and checking the Approver's To Do list. | Approver | 1. Log into Coupa as user whose approval is required. 2. Look for open approval requests in "To Do's" 3. Review the request 4. Click the button "Approve" 5. Confirm the requisition is routed to the next approver in the approval chain. 6. Repeat steps 1-5 for all subsequent approvers. 7. Ensure item passes through to become a PO and is numbered in sequence | Requisition is approved and PO is created | PO #
4.2 | Perform approval using email | Process Approval via email | Approver | 1. Login to Coupa using your user ID; on the Home page, select a Requisition that was previously created and copy it into a new Requisition. 2. Note the first approver; have the System Admin change that User Profile to your email address. Have the System Admin verify that the approver has Email Notifications turned on for Approvals. 3. Click "Submit for Approval". 4. Log in as a Buyer and resolve the Pending Buyer Action issues. Click 'Send to Next Approver' when done. 5. Verify you received an email from the system. 6. Review the email and click the Approval button. 7. Confirm on the requisition that your approval is reflected, and that a notification has been sent to the next approver in the approval chain. | Requisition is approved and PO is created | PO #
4.3 | Perform approval using iPhone (Coupa app) | Process Approval via iPhone | Approver | 1. Login to Coupa using your user ID; on the Home page, select a Requisition that was previously created and copy it into a new Requisition. 2. Note the first approver; if it is not Brad Biller, add Brad as the first approver. 3. Click "Submit for Approval". 4. Log in as a Buyer and resolve the Pending Buyer Action issues. Click 'Send to Next Approver' when done. 5. Verify with Brad that he received a notification from the system. 6. Brad to review the notification and click the Approval button. 7. Confirm on the requisition that Brad's approval is reflected, and that a notification has been sent to the next approver in the approval chain. | Requisition is approved and PO is created | PO #
4.4 | Perform approval using other type of PDA | Process Approval via PDA | Approver | 1. Login to Coupa using your user ID; on the Home page, select a Requisition that was previously created and copy it into a new Requisition. 2. Note the first approver; have the System Admin change that User Profile to your email address. Have the System Admin verify that the approver has Email Notifications turned on for Approvals. 3. Click "Submit for Approval". 4. Log in as a Buyer and resolve the Pending Buyer Action issues. Click 'Send to Next Approver' when done. 5. Verify you received an email from the system on your PDA. 6. Review the email and click the Approval button. 7. Confirm on the requisition that your approval is reflected, and that a notification has been sent to the next approver in the approval chain. | Requisition is approved and PO is created | PO #
4.5 | Delegate Approvals | Process Approval by logging into Coupa and checking the Approver's To Do list. | Approver | 1. Login to Coupa using your user ID; on the Home page, select a Requisition that was previously created and copy it into a new Requisition. 2. Note the first approver; have the System Admin update the Delegate Approvals page for that approver with your User Id. 3. Click "Submit for Approval". 4. Log in as a Buyer and resolve the Pending Buyer Action issues. Click 'Send to Next Approver' when done. 5. Verify you received an email from the system. 6. Review the email and click the Approval button. 7. Confirm on the requisition that your approval is reflected, and that a notification has been sent to the next approver in the approval chain. | Requisition is approved and PO is created | PO #
4.6 | Reminder Notifications and Escalations (will take X hours) | Process Approval by logging into Coupa and accessing the Approver's Inbox. | Approver | 1. Login to Coupa using your user ID; on the Home page, select a Requisition that was previously created and copy it into a new Requisition. 2. Note the first approver; have the System Admin change that User Profile to your email address. Have the System Admin verify that the approver has Email Notifications turned on for Approvals. 3. Click "Submit for Approval". 4. Log in as a Buyer and resolve the Pending Buyer Action issues. Click 'Send to Next Approver' when done. 5. Verify you received an email from the system. 6. Do not act on the Approval Notification. 7. After you receive the reminder in 3 days, use it to approve the requisition. 8. Confirm on the requisition that your approval is reflected, and that a notification has been sent to the next approver in the approval chain. | Requisition is approved and PO is created | PO #
4.7 | Approval chain routing | Process Approval by logging into Coupa and accessing the Approver's Inbox. | Approver | 1. Enter a Requisition line meeting the first of the conditions below. (if unsure of condition, see System Admin for more information). 2. Save the req, and verify the approval chain / error that is generated. 3. Change the requisition to reflect the next condition, and re-save the requisition. 4. Verify that the Approval chain is updated based on the new requisition's information, and is correct . 5.Repeat for all Approval Chains, confirm the accuracy of the approval chain. Vendor Division Error - Commercial, Error - Project Field Blank, Error - Project w/Blank Activity, Commodity - Technology, >$25000 - Buyer Hold | Requisition approval chain is properly created or error message is properly generated.
4.8 | Req with Approval Denied - To Do List | Process Denial by logging into Coupa and checking the Approver's To Do list. | Approver | 1. Login to Coupa using your user ID; on the Home page, select the Requisition from TC 9.63 and copy it into a new Requisition. 2. Note the first approver. 3. Click "Submit for Approval". 4. Log in as a Buyer and resolve the Pending Buyer Action issues. Click 'Send to Next Approver' when done. 5. Log in as the first approver, and approve the requisition from the To Do list. 6. Confirm on the requisition that your approval is reflected, and that a notification has been sent to the next approver in the approval chain. 7. Log in as the second approver (verify that Online notification is turned on) and look up the Requisition Approval on the To Do List. Enter a comment and deny the requisition. 8. Verify that a denial email was sent to you as the requester, and that there is a notification in your My Account My Inbox. | Requisition is approved and PO is created | PO #
4.9 | Req with Approval Denied - Inbox | Process Denial by logging into Coupa and accessing the Approver's Inbox. | Approver | 1. Login to Coupa using your user ID; on the Home page, select the Requisition from TC 9.63 and copy it into a new Requisition. 2. Note the first approver. 3. Click "Submit for Approval". 4. Log in as a Buyer and resolve the Pending Buyer Action issues. Click 'Send to Next Approver' when done. 5. Log in as the first approver, and approve the requisition from the My Account My Inbox link. 6. Confirm on the requisition that your approval is reflected, and that a notification has been sent to the next approver in the approval chain. 7. Log in as the second approver (verify that Online notification is turned on) and look up the Requisition Approval in the My Account My Inbox. Enter a comment and deny the requisition. 8. Verify that a denial email was sent to you as the requester, and that there is a notification in your My Account My Inbox. | Requisition is approved and PO is created | PO #
4.10 | Req with Approval Denied - Email | Process Denial by Email | Approver | 1. Login to Coupa using your user ID; on the Home page, select the Requisition from TC 9.63 and copy it into a new Requisition. 2. Note the first approver; have the System Admin change that User Profile to your email address. Have the System Admin verify that the approver has Email Notifications turned on for Approvals. 3. Click "Submit for Approval". 4. Log in as a Buyer and resolve the Pending Buyer Action issues. Click 'Send to Next Approver' when done. 5. Verify you received an email from the system. 6. Review the email and click the Deny button. 7. Confirm on the requisition that your denial is reflected. 8. Verify that a denial email was sent to you as the requester, and that there is a notification in your My Account My Inbox. | Requisition is approved and PO is created | PO #

## Case 5 PO Processing
Test Case #9 |  | Process Purchase Orders
Description
# | Test Scenario | Test Script | Role | Test Steps | Expected Result | Actual Result | Tester | Pass/Fail
5.1 | Issue cXML PO | Process Purchase Orders | Buyer | 1.Login to Coupa using your user ID; on the Home page, click on the Orders menu item. 2.Look up a purchase order for a cXML Vendor (typically a punchout vendor). 3. Confirm that it has been transmitted via cXML to the vendor of choice. If not, initiate the process utilizing the Send PO icon. | PO is successfully transmitted to Supplier
5.2 | Issue Email PO | Process Purchase Orders | Buyer | 1.Login to Coupa using your user ID; on the Home page, click on the Orders menu item. 2.Look up a purchase order for a supplier with a transmission method of email. 3. Confirm that it has been transmitted via Email to the proper vendor. If not, initiate the process utilizing the Send PO icon. Contact System Admin to change Email address on Supplier to one you can access in order to review output. | PO is successfully transmitted to Supplier
5.3 | Issue HardCopy PO and Mark as Sent | Process Purchase Orders | Buyer | 1.Login to Coupa using your user ID; on the Home page, click on the Orders menu item. 2.Look up the PO from a vendor with a transmission method of prompt. 3. Manually mark it as sent via the Send PO icon; use the Printer icon to produce a hard copy PO for verification. 4. Verify the Ship To references the Buy on Behalf of individual. | PO is successfully created for Supplier
5.4 | Deliver PO to Supplier set to "Prompt" | Process Purchase Orders | Buyer | 1. Verify that a PO was manually transmitted via cXML and email in the test cases above. 2. If not, enter a new req and take it through to a PO for a cXML Supplier where the PO Method is set to 'Prompt'. Transmit the PO manually. 3. If not, enter a new req and take it through to a PO for a Email Supplier where the PO Method is set to 'Prompt'. Transmit the PO manually. | PO is successfully manually transmitted to a CXML Supplier and an Email Supplier
5.5 | Manually Close PO | Process Purchase Orders | Buyer | 1. Look up any purchase order in the system and use the Close PO icon to manually close it. 2. Confirm no further activity can take place against it. | PO is successfully manually closed.

## Case 6 Service Timesheet Entry
Test Case #11 |  | Service/Timesheet Entry
Description
# | Test Scenario | Test Script | Role | Test Steps | Expected Result | Actual Result | Tester | Pass/Fail
6.1 | Enter Service/Timeshseet for Resource using the CSP | Service/Timesheet Entry | Supplier | 1. Log into CSP using your supplier email address 2. Click on Orders tab and find service order 3. Select action "Create Service/Timesheets" 4. Select line and click "Create Service/Timesheets" 5. Complete timesheet 6. Click "Submit". | Service/Timesheet is sent for approval | Srv/Timesheet Nbr
6.2 | Enter Service/Timesheet for Services Qty using the CSP | Service/Timesheet Entry | Supplier | 1. Log into CSP using your supplier email address 2. Click on Orders tab and find service order 3. Select action "Create Service/Timesheets" 4. Select line and click "Create Service/Timesheets" 5. Enter the qty of services completed and the Actual completion date 6. Click "Submit". | Service/Timesheet is sent for approval | Srv/Timesheet Nbr
6.3 | Enter Service/Timesheet for Services Amt using the CSP | Service/Timesheet Entry | Supplier | 1. Log into CSP using your supplier email address 2. Click on Orders tab and find service order 3. Select action "Create Service/Timesheets" 4. Select line and click "Create Service/Timesheets" 5. Enter the amount of services completed and the Actual completion date 6. Click "Submit". | Service/Timesheet is sent for approval | Srv/Timesheet Nbr
6.4 | Enter Service/Timesheet for Resource using the SAN | Service/Timesheet Entry | Supplier | Not getting SAN email | Service/Timesheet is sent for approval | Srv/Timesheet Nbr
6.5 | Enter Service/Timesheet for Services Qty using the SAN | Service/Timesheet Entry | Supplier | 1. Review emails 2. Open email with title 'Please submit your Service/Time Sheet Entry against Order #XX for Coupa Software' 3. Click on 'Create Service/Timesheet' 4. Enter the qty of services completed and the Actual completion date 5. Click "Submit". | Service/Timesheet is sent for approval | Srv/Timesheet Nbr
6.6 | Enter Service/Timesheet for Services Amt using the SAN | Service/Timesheet Entry | Supplier | 1. Review emails 2. Open email with title 'Please submit your Service/Time Sheet Entry against Order #XX for Coupa Software' 3. Click on 'Create Service/Timesheet' 4. Enter the amount of services completed and the Actual completion date 5. Click "Submit". | Service/Timesheet is sent for approval | Srv/Timesheet Nbr
6.7 | Try to create Service/Timesheet against PO that is soft closed | Service/Timesheet Entry | Supplier | 1.Login to Coupa and soft close a PO 2. Log into the CSP as a supplier 3. Try to create a Service/Timesheet against PO that is soft close. | Not able to create Service/timesheet
6.8 | Enter a manual receipt against a Service PO | Service/Timesheet Entry | Requestor | 1. Log into Coupa using your user ID 2. Access requisition from recent orders or from your spend history. 3. Select the Requisition and click on the truck icon to the right "Receive against Requisition #" 4. Enter the full quantity ordered for each line to receive in full. 5. Click "Save". | Receipt is created | Receipt Nbr

## Case 7 Srv TS Approvals
Test Case #8 |  | Service/ Timesheet Approvals
Description
# | Test Scenario | Test Script | Role | Test Steps | Expected Result | Actual Result | Tester | Pass/Fail
7.1 | Approve Service/timesheet | Process Approval by logging into Coupa and checking the Approver's To Do list. | Approver | 1. Log into Coupa as user whose approval is required. 2. Look for open approval requests in "To Do's" 3. Review the request 4. Provide a quality assesment 5. Click the button "Approve" 6. Confirm the service/timesheet is routed to the next approver in the approval chain. 7. Repeat steps 1-5 for all subsequent approvers. 8. Ensure service/timesheet has status approved 9. Ensure PO receipt and confirmed values updated based on amt/qty received | Service / Timesheet approved. Receipt and confirmed amt/qty updated in PO | Receipt #
7.2 | Perform approval using email | Process Approval via email | Approver | 1. Login to CSP as supplier and submit another service/timesheet 2. Check approver for service/timesheet 3. Verify you received an email from the system. 4. Review the email and verify that the total / total qty at the bottom reflects amt/qty already received. 5. Provide quality assesment and click the Approval button. 6. Ensure PO receipt and confirmed values updated based on amt/qty received | Service / Timesheet approved. Receipt and confirmed amt/qty updated in PO | Receipt #
7.3 | Reminder Notifications and Escalations (will take X hours) | Process Approval by logging into Coupa and accessing the Approver's Inbox. | Approver | 1. . Login to CSP as supplier and submit another service/timesheet 2. Check approver for service/timesheet 3. Verify you received an email from the system. 4. Do not act on the Approval Notification. 5. After you receive the reminder in 3 days, use it to approve the service/timesheet 6. Ensure PO receipt and confirmed values updated based on amt/qty received | Service / Timesheet approved. Receipt and confirmed amt/qty updated in PO | Receipt #
7.4 | Req with Approval Denied - To Do List | Process Denial by logging into Coupa and checking the Approver's To Do list. | Approver | 1. Log into Coupa as user whose approval is required. 2. Look for open approval requests in "To Do's" 3. Review the request 4. Enter a comment and deny the service/timesheet 5. Verify that a denial email was sent to the supplier | Approval denied
7.5 | Req with Approval Denied - Inbox | Process Denial by logging into Coupa and accessing the Approver's Inbox. | Approver | 1. Log into Coupa as user whose approval is required. 2. Look for open approval requests in "Inbox" 3. Review the request 4. Enter a comment and deny the service/timesheet 5. Verify that a denial email was sent to the supplier | Approval denied
7.6 | Req with Approval Denied - Email | Process Denial by Email | Approver | 1. Log into Coupa as user whose approval is required. 2. Note the first approver; have the System Admin change that User Profile to your email address. Have the System Admin verify that the approver has Email Notifications turned on for Approvals. 3. Verify you received an email from the system. 4. Review the email and click the Deny button. 5. Confirm on the service/timesheet that your denial is reflected. 6. Verify that a denial email was sent to the supplier | Approval denied

## Case 8 Invoice Processing
Test Case #12 |  | Invoice Processing and Matching
Description
# | Test Scenario | Test Script | Role | Test Steps | Expected Result | Actual Result | Tester | Pass/Fail
8.1 | Enter Invoices against a purchase order. | Invoice Processing and Matching | AP User | 1. Log into Coupa using your user ID 2. Click orders at the top of the screen. 3. Using the advanced search option, navigate to the order in question. 4. Select the gold coins icon to create an invoice. 5. Enter the invoice number and additional charges. 6. Validate the line items, then select submit. 7. Confirm that the invoice is submitted, and has moved to approved status. | Invoice Created | Invoice Nbr
8.2 | Invoice for Qty greater than received | Invoice Processing and Matching |  | 1. Log into Coupa using your user ID 2. Click orders at the top of the screen. 3. Using the advanced search option, navigate to the services qty order which has not been received (assuming 3-way match requirement) 4. Select the gold coins icon to create an invoice. 5. Enter the invoice number and additional charges. 6. Validate the line items, then select submit. 7. Confirm that the invoice is submitted, and has moved to Pending receipt status. 8. Login as supplier and submit a service/timesheet to match invoice and submit 9. Log in as approver and approve the service/timesheet 10. Confirm that the invoice is has moved to approved status | Invoice Created | Invoice Nbr
8.3 | Monthly invoice against weekly timesheets | Invoice Processing |  | 1. Log into Coupa using your user ID 2. Create request for a service - type resource for a months worth of work 3. Approve request to create a PO 4. Login as supplier to CSP and submit a service/timesheet for a week, stating resource name 5. Repeat 3 more times so to have 4 weeks worth of service/timesheets submitted 6. Log in as approver and approve all service/timesheet 7. Login as supplier to CSP, flip the PO to create the invoice and submit 8. Check Invoice status approved | Invoice Created | Invoice Nbr
8.4 | Invoice / receipt value greater than PO value | Invoice Processing | AP User | 1. Log into Coupa using your user ID 2. Create request for a service - type amount 3. Approve request to create a PO 4. Login as supplier to CSP and submit a service/timesheet for a week, so to exceed the amount on the PO. Amount should exceed tolerances set. 5. Log in as approver and approve all service/timesheet 7. Login as supplier to CSP, flip the PO to create the invoice and submit. (Invoice amount to be the same as on service/timesheet) 8. Check Invoice status is pending approval due to tolerance being exceeded | Invoice status pending approval | Invoice Nbr
8.5 | Additional charges added to invoice | Invoice Processing | AP User | 1. Log into Coupa using your user ID 2. Create request for a service - type amount 3. Approve request to create a PO 4. Login as supplier to CSP and submit a service/timesheet for a week, Amount entered should be same as on PO 5. Log in as approver and approve all service/timesheet 7. Login as supplier to CSP, flip the PO to create the invoice. Amount to equal PO, but enter additional charges for materials consumed. (Ensure exceeds tolerances set) 8. Check Invoice status is pending approval due to tolerance being exceeded | Invoice status pending approval | Invoice Nbr

## Case 9 Navigation
Test Case #14 |  | Navigation
Description
# | Test Scenario | Test Script | Role | Test Steps | Expected Result | Actual Result | Tester | Pass/Fail
9.1 | Service / Timesheet tab | Navigation | Admin | Login as Administrator and click on orders tab Navigate to Service/Timesheet tab Ensure can review service/timesheets, create a view and export a file
9.2 | Service / Timesheet Lines tab | Navigation | User | Login as Administrator and click on orders tab Navigate to Service/Timesheet Lines tab Ensure can review service/timesheets, create a view and export a file
9.3 | View receipt and confirmation from Order | Navigation | User | Login as Administrator and click on orders tab Select a service order with an approved service/timesheet Click on receipt amount to view the receipt documents Click on the confirmation amount to view the Service/Timesheet documents